## Cover
[ SOP(Standard Operation Procedure) ]
개정이력표
버전 | 날짜 | 내 용 | 담당자
2 | 2025.08.24 | 최초 작성 | 현지수
7.5 | 2025.09.02 | root계정에서 gpssh 사용, gpfailover 및 gpkrutil 설정 | 현지수
활용 용도 및 작성 방법
설치, 증설, 재구성, 유지보수(Upgrade, Break/Fix 포함), 변경작업, 프로젝트 세부 작업 계획과 관련된 표준화된 작업 문서로 활용 가능
장애발생 후 긴급 서비스 정상화/안정화를 목적으로 하는 경우는 제외

## Install_7.5_RHEL9
작 업 계 획 서
작업 내용 | GPDB 7.x Installation on RHEL9
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
자료 URL | https://github.com/gpdbkr/gpkrutil
범례 | [~]# : root 계정으로 실행
[~]$ : gpadmin 계정으로 실행
작 업 계 획
날짜 | 대분류 | 설치 구분 | Service | Task | 중분류 | 작업 | 소분류 | 확인 사항 | 비고
| (HW/SW/ETC) |  | (Up/Down) | # | (Task) | 노드 | (세부 작업 내용, Commands 포함)
| SW | OS | Down | 1 | 시스템 정보 확인 | cdw | [~]# uname -r
[~]# cat /etc/redhat-release
| SW | OS | Down | 2 | root 계정 gpssh 사용 설정 | cdw |  | [~]# ls -al /data/staging
…
[8 empty] | drwxr-xr-x. 2 root root 4096 Aug 28 22:23 gpdb752_rh9 | * gpdb, gpcc, pxf 설치 파일을 /data/staging/gpdb{버전}_{OS} 폴더에 업로드
[8 empty] | drwxr-xr-x. 2 root root 4096 Aug 28 22:25 install_pkg | * gpdb 설치에 필요한 파일을 /data/staging/install_pkg 폴더에 업로드
[8 empty] | [~]# ls -al /data/staging/install_pkg/ | * URL - https://github.com/zhyun-pivotal/gpdb6_install
-rwxr-xr-x. 1 gpadmin gpadmin 252 Aug 28 23:11 crt_service_monitoring.sh
-rwxr-xr-x. 1 gpadmin gpadmin 3248 Aug 28 23:11 crt_expand_map_gp7.sh
-rwxr-xr-x. 1 gpadmin gpadmin 623 Aug 28 23:12 gpcc.conf
-rwxr-xr-x. 1 gpadmin gpadmin 18253 Aug 28 23:11 gpdb7_install_result_check.sh
-rw-r--r--. 1 gpadmin gpadmin 2980 Aug 28 23:12 gpfailover_setup_gp7.tar.gz
[8 empty] | -rw-r--r-- 1 gpadmin gpadmin 411256 Aug 29 20:46 gpkrutil-main.zip | * gpkrutil download URL - https://github.com/gpdbkr/gpkrutil
-rwxr-xr-x. 1 gpadmin gpadmin 5835 Aug 28 23:12 remotechk_gp7.sh
[7 empty] | (1) GPDB 의존성 패키지 설치 |  | * root 계정으로 gpssh 기능 사용을 위해서 master 노드에 우선 GPDB 엔진 설치
[~]# yum install -y chrony compat-openssl11 dstat gdb java-11-openjdk.x86_64
[~]# yum install -y lsof m4 net-tools strace tcpdump python3-setuptools tk rsync
(2) GPDB rpm 설치
[~]# ls -al /data/staging/gpdb752_rh9/greenplum-db*.rpm
-rw-r--r--. 1 root root 277869142 Aug 28 22:23 /data/staging/gpdb752_rh9/greenplum-db-7.5.2-el9-x86_64.rpm
[~]# yum install -y /data/staging/gpdb752_rh9/greenplum-db-7.5.2-el9-x86_64.rpm
[~]# ls -al /usr/local ¦ grep greenplum
lrwxrwxrwx. 1 root root 29 Aug 28 22:41 greenplum-db -> /usr/local/greenplum-db-7.5.2
drwxr-xr-x. 11 root root 4096 Aug 28 22:41 greenplum-db-7.5.2
(3) gpssh 사용 가능여부 확인
[7 empty] | [~]# source /usr/local/greenplum-db/greenplum_path.sh |  | * root 계정으로 gpssh 사용을 위해서는 greenplum_path.sh을 적용해야 함
[~]# gpssh-exkeys --version
gpssh-exkeys version 7.5.2 build commit:3895899b5b368e7c44765a6efb12e9e815742327
| SW | OS | Down | 3 | root 계정 키교환(1/2) | cdw | (1) /etc/hosts 파일에 클러스터의 모든 서버 목록 업데이트
[5 empty] | (real hostname) |  | [~]# vi /etc/hosts
[~]# cat /etc/hosts
…
172.16.142.121 rk9gc1 cdw
172.16.142.122 rk9gc2 scdw
172.16.142.123 rk9gs1 sdw1
…
(2) hostfile 생성(real & alias) and known hosts 파일에 서버 목록 업데이트
[~]# cd /data/staging
[~]# vi hostfile
[~]# cat hostfile
rk9gc1
rk9gc2
rk9gs1
…
[~]# vi hostfile_alias
[~]# cat hostfile_alias
cdw
scdw
sdw1
…
(3) ssh key 생성
[~]# ssh-keygen -t rsa -b 4096
Generating public/private rsa key pair.
Enter file in which to save the key (/root/.ssh/id_rsa):
Enter passphrase (empty for no passphrase):
Enter same passphrase again:
Your identification has been saved in /root/.ssh/id_rsa
Your public key has been saved in /root/.ssh/id_rsa.pub
…
(4) ssh key 교환 스크립트 생성
[~]# vi sshkey_copy.sh
[8 empty] | [~]# cat sshkey_copy.sh | * sshkey_copy.sh 파일 전체 내용은 sshkey_copy sheet 참조
#!/bin/bash
source ~/.bashrc
HOST_LIST=`cat /data/staging/hostfile`
…
(5) ssh key 교환(real hostname)
[7 empty] | [~]# sh sshkey_copy.sh hostfile |  | * GPDB 클러스터의 모든 노드 대상으로 접속 여부와 암호 입력 필요
/usr/bin/ssh-copy-id: INFO: Source of key(s) to be installed: "/root/.ssh/id_rsa.pub"
The authenticity of host 'rk9gc1 (172.16.142.121)' can't be established.
ED25519 key fingerprint is SHA256:JXyQxqho0ivTvY5EA+JXaN+fI9ZNwL4Jj1F7U8FZuLc.
Are you sure you want to continue connecting (yes/no/[fingerprint])? yes
/usr/bin/ssh-copy-id: INFO: attempting to log in with the new key(s), to filter out any that are already installed
/usr/bin/ssh-copy-id: INFO: 1 key(s) remain to be installed -- if you are prompted now it is to install the new keys
root@rk9gc1's password:
…
| SW | OS | Down | 4 | root 계정 키교환(2/2) | cdw | (1) ssh key 교환(alias hostname)
[5 empty] | (alias hostname) |  | [~]# sh sshkey_copy.sh hostfile_alias |  | * GPDB 클러스터의 모든 노드 대상으로 접속 여부 입력 필요
/usr/bin/ssh-copy-id: INFO: Source of key(s) to be installed: "/root/.ssh/id_rsa.pub"
The authenticity of host 'cdw (172.16.142.121)' can't be established.
ED25519 key fingerprint is SHA256:JXyQxqho0ivTvY5EA+JXaN+fI9ZNwL4Jj1F7U8FZuLc.
Are you sure you want to continue connecting (yes/no/[fingerprint])? yes
/usr/bin/ssh-copy-id: INFO: attempting to log in with the new key(s), to filter out any that are already installed
/usr/bin/ssh-copy-id: WARNING: All keys were skipped because they already exist on the remote system.
(if you think this is a mistake, you may want to use -f option)
(2) gpssh 접속 여부 확인
[7 empty] | [~]# source /usr/local/greenplum-db/greenplum_path.sh |  | * root 계정으로 gpssh 사용을 위해서는 greenplum_path.sh을 적용해야 함
[~]# gpssh -f /data/staging/hostfile
=> hostname
=> ls -al /root/.ssh
=> exit
[~]# gpssh -f /data/staging/hostfile_alias
=> hostname
=> exit
| SW | OS | Down | 5 | root 계정 gpssh alias 등록 | cdw | (1) alias 등록을 위한 segment real hostname을 등록한 hostfile_seg 파일 생성
[~]# cd /data/staging
[~]# vi hostfile_seg
[~]# cat hostfile_seg
rk9gs1
rk9gs2
[~]# vi hostfile_seg_alias
[~]# cat hostfile_seg_alias
sdw1
sdw2
(2) root 계정에 alias 등록
[~]# vi ~/.bashrc
[~]# cat ~/.bashrc
…
### Greenplum Setting
alias gpsync='source /usr/local/greenplum-db/greenplum_path.sh;gpsync'
alias gpssh='source /usr/local/greenplum-db/greenplum_path.sh;gpssh'
alias gpssh-exkeys='source /usr/local/greenplum-db/greenplum_path.sh;gpssh-exkeys'
alias all='gpssh -f /data/staging/hostfile'
alias seg='gpssh -f /data/staging/hostfile_seg'
[~]# source ~/.bashrc
| SW | OS | Down | 6 | gpssh 접속 확인 | cdw | [~]# all
=> hostname
=> exit
| SW | RHEL8 | Down | 7 | 필수 O/S 패키지 설치 | cdw | [~] all |  | * RHEL 7.x의 ntp와 stack은 RHEL 9.x 에서 chrony와 gdb로 대체 됩니다.
[7 empty] | => yum install -y chrony compat-openssl11 dstat gdb java-11-openjdk.x86_64 |  | * coordinator 노드는 TASK2에서 필수패키지를 설치했기 때문에 경고 메시지가 나올 수 있음
=> yum install -y lsof m4 net-tools strace tcpdump python3-setuptools tk rsync
=> exit
| SW | OS | Down | 8 | host file 배포 | cdw | (1) /etc/hosts 내용 확인
[~]# cat /etc/hosts
[~]# gpsync -f /data/staging/hostfile /etc/hosts =:/etc/
(2) 배포 결과 확인
[~]# all
=> cat /etc/hosts
=> exit
| SW | OS | Down | 9 | 방화벽 해제 여부 확인 | cdw | (1) 방화벽 실행 여부 확인(실행 중일 때의 결과 예제)
[~]# all
=> sestatus
[rk9gc2] SELinux status: enabled
[rk9gc2] SELinuxfs mount: /sys/fs/selinux
[rk9gc2] SELinux root directory: /etc/selinux
[rk9gc2] Loaded policy name: targeted
[rk9gc2] Current mode: enforcing
[rk9gc2] Mode from config file: enforcing
[rk9gc2] Policy MLS status: enabled
[rk9gc2] Policy deny_unknown status: allowed
[rk9gc2] Memory protection checking: actual (secure)
[rk9gc2] Max kernel policy version: 33
=> cat /etc/selinux/config ¦ grep "SELINUX="
[rk9gc2] # SELINUX= can take one of these three values:
[rk9gc2] # NOTE: In earlier Fedora kernel builds, SELINUX=disabled would also
[rk9gc2] SELINUX=enforcing
=> exit
| SW | OS | Down | 10 | 방화벽 해제 | cdw | (1) 방화벽 설정 해제 상태로 변경 및 방화벽 해제
[~]# all
=> sed -i 's/SELINUX=enforcing/SELINUX=disabled/g' /etc/selinux/config
=> cat /etc/selinux/config ¦ grep "SELINUX="
[rk9gs2] # SELINUX= can take one of these three values:
[rk9gs2] # NOTE: Up to RHEL 8 release included, SELINUX=disabled would also
[rk9gs2] SELINUX=disabled
=> systemctl stop firewalld.service
=> systemctl disable firewalld.service
[rk9gs4] Removed /etc/systemd/system/multi-user.target.wants/firewalld.service.
[rk9gs4] Removed /etc/systemd/system/dbus-org.fedoraproject.FirewallD1.service.
=> systemctl status firewalld.service
[rk9gs2] ○ firewalld.service - firewalld - dynamic firewall daemon
[rk9gs2] Loaded: loaded (/usr/lib/systemd/system/firewalld.service; disabled; preset: enabled)
[rk9gs2] Active: inactive (dead)
[rk9gs2] Docs: man:firewalld(1)
[rk9gs2]
[rk9gs2] Aug 29 11:41:12 rk9gs2 systemd[1]: Starting firewalld - dynamic firewall daemon...
[rk9gs2] Aug 29 11:41:12 rk9gs2 systemd[1]: Started firewalld - dynamic firewall daemon.
[rk9gs2] Aug 29 11:45:14 rk9gs2 systemd[1]: Stopping firewalld - dynamic firewall daemon...
[rk9gs2] Aug 29 11:45:14 rk9gs2 systemd[1]: firewalld.service: Deactivated successfully.
=> exit
(2) 서버 재기동 (segments 부터 순차적으로 리부팅)
[~]# seg
=> init 6
=> exit
[~]# ssh scdw init 6
[~]# init 6
(3) 서버 재기동 후 방화벽 해제 확인
[~]# all
=> sestatus
[rk9gs4] SELinux status: disabled
=> cat /etc/selinux/config ¦ grep "SELINUX="
[rk9gs2] # SELINUX= can take one of these three values:
[rk9gs2] # NOTE: Up to RHEL 8 release included, SELINUX=disabled would also
[rk9gs2] SELINUX=disabled
=> exit
| SW | OS | Down | 11 | sysctl.conf 설정 | cdw | [~]# vi /root/set_sysctl_less64.sh |  | * 메모리 64GB 이상인 경우 set_sysctl sheet의 set_sysctl_more64.sh 항목 참조
[5 empty] | (메모리 64GB 이상/미만 분기) |  |  | [~]# cat /root/set_sysctl_less64.sh <<< 상세 내용은 set_sysctl sheet 참조 | -> 파라메터 중 시스템메모리 값에 따라 계산이 필요한 파라메터는 메모리 설정값 확인 필요
echo "" >> /etc/sysctl.conf
echo "### setting up a server with less than 64GB of memory ###" >> /etc/sysctl.conf
echo "kernel.shmall = "$(expr $(getconf _PHYS_PAGES) / 2) >> /etc/sysctl.conf
echo "kernel.shmmax = "$(expr $(getconf _PHYS_PAGES) / 2 \* $(getconf PAGE_SIZE)) >> /etc/sysctl.conf
echo "kernel.shmmni = 32768" >> /etc/sysctl.conf
…
| SW | OS | Down | 12 | sysctl.conf 설정 파일 | cdw | [~]# gpsync -f /data/staging/hostfile /root/set_sysctl_less64.sh =:/root/set_sysctl_less64.sh
[5 empty] | 배포 및 적용 |  | [~]# all
=> chmod +x /root/set_sysctl_less64.sh
=> ls -al /root/set_sysctl_less64.sh
[rk9gs2] -rwxr-xr-x 1 root root 2014 May 24 11:31 /root/set_sysctl_less64.sh
=> sh /root/set_sysctl_less64.sh
=> cat /etc/sysctl.conf
[rk9gs2] kernel.shmall = 464135
[rk9gs2] kernel.shmmax = 1901096960
[rk9gs2] kernel.shmmni = 32768
…
=> sysctl -p
[rk9gs2] kernel.shmall = 464135
[rk9gs2] kernel.shmmax = 1901096960
[rk9gs2] kernel.shmmni = 32768
…
=> exit
| SW | OS | Down | 13 | System Resource Limit 설정 | cdw |  | [~]# ls -al /etc/security/limits.conf | * /etc/security/limits.conf 대체 파일을 이용하여 설정하는 경우도 있음
[8 empty] | -rw-r--r--. 1 root root 2426 Nov 4 2024 /etc/security/limits.conf | -> /etc/security/limits.d/90-nproc.conf file (RHEL/CentOS 6)
[7 empty] | [~]# vi /etc/security/limits.conf |  | -> /etc/security/limits.d/20-nproc.conf file (RHEL/CentOS 7)
[8 empty] | [~]# cat /etc/security/limits.conf ¦ grep -v "#" | -> core 파일 생성을 위한 설정도 추가하였음
root soft nproc unlimited
* soft nofile 524288
* hard nofile 524288
* soft nproc 131072
* hard nproc 131072
* soft core unlimited
| SW | OS | Down | 14 | System Resource Limit 배포 | cdw | [~]# gpsync -f /data/staging/hostfile /etc/security/limits.conf =:/etc/security/limits.conf
[~]# all
=> cat /etc/security/limits.conf ¦ grep -v "#"
=> exit
| SW | RHEL8 | Down | 15 | XFS Mount Options 설정 | cdw | [~]# all |  | * 주의 : 잘못 설정 시 재기동 시 부팅 안되므로 명령어 복사하여 사용!!!
[8 empty] | => cat /etc/fstab ¦ grep -v "#" | RHEL8 환경에서는 nobarrier 옵션이 제거됩니다.
[rk9gs2] /dev/mapper/rl-root / xfs defaults 0 0
[rk9gs2] UUID=0a0c4857-f02f-4eea-ab97-4bbbaf36266a /boot xfs defaults 0 0
[rk9gs2] /dev/mapper/rl-home /home xfs defaults 0 0
[rk9gs2] /dev/mapper/rl-swap none swap defaults 0 0
=> sed -i 's/xfs defaults/xfs nodev,noatime,inode64/g' /etc/fstab
=> sed -i 's/xfs \tdefaults/xfs nodev,noatime,,inode64/g' /etc/fstab
=> cat /etc/fstab ¦ grep "xfs"
[rk9gs2] /dev/mapper/centos-root / xfs nodev,noatime,inode64 0 0
[rk9gs2] UUID=50dd3a09-4f71-4a7d-92ee-ac90812be6a5 /boot xfs nodev,noatime,inode64 0 0
[rk9gs2] /dev/mapper/centos-home /home xfs nodev,noatime,inode64 0 0
…
=> exit
| SW | OS | Down | 16 | Disk I/O 설정 | cdw | (1) Disk I/O 설정값 확인 및 rc.local 상태 체크
[~]# all
[7 empty] | => /sbin/blockdev --getra /dev/sd* |  | * Linux 버전에 따라 매핑되는 디바이스 이름이 다를 수 있으며, 아래와 같이 오류 발생 할 수 있음
[7 empty] | [rk9gs2] 8192 |  | blockdev: cannot open /dev/mapper/vg*: No such file or directory
=> /sbin/blockdev --getra /dev/mapper/rl*
[rk9gs2] 256
=> /sbin/blockdev --getra /dev/mapper/rh*
[rk9gs2] 256
=> /sbin/blockdev --getra /dev/mapper/vg*
[rk9gs2] 256
=> systemctl status rc-local
[rk9gs2] ○ rc-local.service - /etc/rc.d/rc.local Compatibility
[rk9gs2] Loaded: loaded (/usr/lib/systemd/system/rc-local.service; static)
[rk9gs2] Active: inactive (dead)
[rk9gs2] Docs: man:systemd-rc-local-generator(8)
=> exit
(2) Disk I/O 설정 및 rc.local 활성화
[~]# vi /etc/rc.d/rc.local
[8 empty] | [~]# cat /etc/rc.d/rc.local ¦ grep -v "#" | * 매핑이 확인 된 디바이스에 한해서 설정 추가가 필요함
touch /var/lock/subsys/local
/sbin/blockdev --setra 16384 /dev/sd* <<< 설정 추가(CentOS, RHEL)
/sbin/blockdev --setra 16384 /dev/mapper/rl* <<< 설정 추가(Rocky)
/sbin/blockdev --setra 16384 /dev/mapper/rh* <<< 설정 추가(RHEL)
/sbin/blockdev --setra 16384 /dev/mapper/vg* <<< 설정 추가(RHEL)
[~]# gpsync -f /data/staging/hostfile /etc/rc.d/rc.local =:/etc/rc.d/rc.local
[~]# all
=> chmod +x /etc/rc.d/rc.local
=> systemctl start rc-local
=> systemctl enable rc-local
[rk9gs2] The unit files have no installation config (WantedBy=, RequiredBy=, Also=,
[rk9gs2] Alias= settings in the [Install] section, and DefaultInstance= for template
[rk9gs2] units). This means they are not meant to be enabled or disabled using systemctl.
[rk9gs2]
[rk9gs2] Possible reasons for having this kind of units are:
[rk9gs2] • A unit may be statically enabled by being symlinked from another unit's
[rk9gs2] .wants/ or .requires/ directory.
[rk9gs2] • A unit's purpose may be to act as a helper for some other unit which has
[rk9gs2] a requirement dependency on it.
[rk9gs2] • A unit may be started when needed via activation (socket, path, timer,
[rk9gs2] D-Bus, udev, scripted systemctl call, ...).
[rk9gs2] • In case of template units, the unit is meant to be enabled with some
[rk9gs2] instance name specified.
=> systemctl status rc-local
[rk9gs2] ● rc-local.service - /etc/rc.d/rc.local Compatibility
[rk9gs2] Loaded: loaded (/usr/lib/systemd/system/rc-local.service; enabled-runtime; preset: disabled)
[rk9gs2] Active: active (exited) since Fri 2025-08-29 12:06:51 KST; 55s ago
[rk9gs2] Docs: man:systemd-rc-local-generator(8)
[rk9gs2] CPU: 6ms
[rk9gs2]
[rk9gs2] Aug 29 12:06:51 rk9gs2 systemd[1]: Starting /etc/rc.d/rc.local Compatibility...
[rk9gs2] Aug 29 12:06:51 rk9gs2 systemd[1]: Started /etc/rc.d/rc.local Compatibility.
=> exit
| SW | OS | Down | 17 | Disk I/O scheduler 와 | cdw | [~]# all |  | * 주의 : gpsync 명령어로 대상 파일을 copy하면 안됨!!!
[5 empty] | Transparent Huge Pages 설정 |  | => grubby --update-kernel=ALL --args="elevator=none" |  | * RHEL9 elevator 설정 옵션은 storage type에 따라 다음과 같이 분류됨
[7 empty] | => grubby --update-kernel=ALL --args="transparent_hugepage=never" |  | -> NVME or SSD : none / Other storage : mq-deadline
=> grubby --info=ALL ¦ grep "elevator"
[rk9gs2] args="ro crashkernel=1G-4G:192M,4G-64G:256M,64G-:512M resume=/dev/mapper/rl-swap rd.lvm.lv=rl/root rd.lvm.lv=rl/swap elevator=none transparent_hugepage=never"
[rk9gs2] args="ro crashkernel=1G-4G:192M,4G-64G:256M,64G-:512M resume=/dev/mapper/rl-swap rd.lvm.lv=rl/root rd.lvm.lv=rl/swap elevator=none transparent_hugepage=never"
=> exit
| SW | OS | Down | 18 | IPC Object Removal | cdw | (1) 설정 파일 변경 |  | * 설정값 설명 (MaxStartups 10:30:200)
[5 empty] | SSH Connection Threshold |  | [~]# all |  | -> 인증되지 않은 접속을 최대 몇개까지 받아들일 것인지 설정하는 파라메터
[5 empty] | 설정 |  | => sed -i '/RemoveIPC/s/^#//g' /etc/systemd/logind.conf |  | -> '10:30:200'은 '초기수:거부확률:최대수'를 의미함
[7 empty] | => sed -i '/MaxStartups/s/\#MaxStartups 10:30:100/MaxStartups 10:30:200/g' /etc/ssh/sshd_config |  | -> Instance per node 갯수가 16개를 넘어가면 '40:30:800'으로 설정하여 ssh 에러 예방
=> sed -i '/MaxSessions/s/\#MaxSessions 10/MaxSessions 200/g' /etc/ssh/sshd_config
(2) 변경 파일 배포 및 결과 확인
=> cat /etc/systemd/logind.conf ¦ grep IPC ¦ grep -v "#"
[rk9gc2] RemoveIPC=no
=> cat /etc/ssh/sshd_config ¦ egrep "MaxStartups¦MaxSessions" ¦ grep -v "#"
[rk9gc2] MaxSessions 200
[rk9gc2] MaxStartups 10:30:200
=> exit
| SW | RHEL8 | Down | 19 | Synchronizing System Clocks | cdw | (1) chrony 설치 여부 확인 |  | * 설정 권장 유형
[5 empty] | 설정 |  | [~]# all |  | -> cdw 설정 : 1차 외부
[7 empty] | => rpm -qa chrony |  | -> scdw 설정 : 1차 cdw / 2차 외부
[7 empty] | => exit |  | -> sdw 설정 : 1차 cdw / 2차 scdw
[7 empty] | (2) ntp 설정 및 배포 (IP는 고객사 환경에 맞춰서 설정) |  | -> 고객 환경에 따라 모든 서버가 동일한 time server를 설정해도 됨
[7 empty] | [~]# vi /etc/chrony.conf |  | -> burst 옵션은 private ntp 서버에만 사용해야 함
[~]# cat /etc/chrony.conf (sample)
server 192.28.194.1 prefer burst iburst <<< private ntp 서버 예제
server asia.pool.ntp.org iburst <<< public ntp server 예제
pool 2.rhel.pool.ntp.org iburst <<< public ntp pool 예제
[~]# gpsync -f /data/staging/hostfile /etc/chrony.conf =:/etc/chrony.conf
(3) chrony 시작 및 자동 구동 설정
[~]# all
=> systemctl enable chronyd
=> systemctl start chronyd
=> timedatectl
[rk9gs2] Local time: Fri 2025-08-29 12:13:03 KST
[rk9gs2] Universal time: Fri 2025-08-29 03:13:03 UTC
[rk9gs2] RTC time: Fri 2025-08-29 03:13:03
[rk9gs2] Time zone: Asia/Seoul (KST, +0900)
[rk9gs2] System clock synchronized: yes
[rk9gs2] NTP service: active
[rk9gs2] RTC in local TZ: no
=> chronyc sources -v
[rk9gc2] MS Name/IP address Stratum Poll Reach LastRx Last sample
[rk9gc2] ===================================================================
[rk9gc2] ^- x.ns.gin.ntt.net 2 6 377 5 -9659us[ +23ms] +/- 104ms
[rk9gc2] ^- 122x215x240x52.ap122.ftt> 2 6 377 0 -64ms[ -64ms] +/- 100ms
[rk9gc2] ^* v4.cloud.ntp.admtan.jp 2 6 377 1 -3683us[ +30ms] +/- 43ms
[rk9gc2] ^+ 108.160.132.224.vultruse> 2 6 377 4 +1505us[ +34ms] +/- 73ms
=> exit
| SW | OS | Down | 20 | 클러스터 서버 재시작 | cdw | (1) Segments 노드 재기동 (cdw 서버에서 수행)
[~]# seg
=> sync;sync;sync
=> init 6
=> exit
(2) cdw, scdw 노드 재기동 (각 서버에서 수행)
[~]# ssh scdw
[~]# sync;sync;sync
[~]# init 6
Connection to scdw closed.
[~]# sync;sync;sync
[~]# init 6
| SW | OS | Down | 21 | OS 설정값 확인 | cdw | [~]# all
=> uptime
=> grubby --info=ALL ¦ grep "elevator"
=> /sbin/blockdev --getra /dev/sd*
=> /sbin/blockdev --getra /dev/mapper/rl*
=> /sbin/blockdev --getra /dev/mapper/rh*
=> /sbin/blockdev --getra /dev/mapper/vg*
=> ulimit -Sa ¦ egrep "open¦processes¦core"
=> ulimit -Ha ¦ egrep "open¦processes¦core"
=> cat /etc/fstab ¦ egrep "xfs"
=> systemctl status chronyd
=> exit
| SW | GPDB | Down | 22 | gpadmin 계정 생성 및 확인 | cdw | [~]# all
=> groupadd -g 1001 gpadmin
=> useradd -u 1001 -g gpadmin gpadmin
=> cat /etc/passwd ¦ grep gpadmin
[rk9gs2] gpadmin:x:1001:1001::/home/gpadmin:/bin/bash
=> cat /etc/group ¦ grep gpadmin
[rk9gs2] gpadmin:x:1001:
[7 empty] | => echo 'changeme' ¦ /usr/bin/passwd --stdin 'gpadmin' |  | * 모든 클러스터 노드의 gpadmin 계정 암호를 일괄로 설정하는 방법
[rk9gc2] Changing password for user gpadmin.
[rk9gc2] passwd: all authentication tokens updated successfully.
=> exit
| SW | GPDB | Down | 23 | gpdb rpm 배포 | cdw | [~]# gpsync -f /data/staging/hostfile /data/staging/gpdb752_rh9/greenplum-db-7.5.2-el9-x86_64.rpm =:/home/gpadmin/greenplum-db-7.5.2-el9-x86_64.rpm
[~]# all
=> ls -al /home/gpadmin/greenplum-db-7.5.2-el9-x86_64.rpm
[rk9gs2] -rw-r--r-- 1 root root 277869142 Aug 29 12:18 /home/gpadmin/greenplum-db-7.5.2-el9-x86_64.rpm
=> exit
| SW | GPDB | Down | 24 | gpdb rpm 설치 | cdw | [~]# all
=> cd /home/gpadmin
=> ls -al *.rpm
[rk9gs2] -rw-r--r-- 1 root root 277869142 Aug 29 12:18 greenplum-db-7.5.2-el9-x86_64.rpm
[7 empty] | => yum install -y ./greenplum-db-7.5.2-el9-x86_64.rpm |  | * yum을 이용하여 설치하면 의존성 있는 패키지를 모두 같이 설치함
…
[rk9gs1] systemtap-sdt-devel-5.2-2.el9.x86_64 unzip-6.0-58.el9_5.x86_64
[rk9gs1] zip-3.0-35.el9.x86_64
[rk9gs1]
[rk9gs1] Complete!
=> exit
| SW | GPDB | Down | 25 | gpdb rpm 설치 확인 | cdw | [~]# all
=> ls -al /usr/local ¦ grep greenplum
[rk9gs2] lrwxrwxrwx 1 root root 29 Aug 29 12:22 greenplum-db -> /usr/local/greenplum-db-7.5.2
[rk9gs2] drwxr-xr-x 11 root root 4096 Aug 29 12:22 greenplum-db-7.5.2
=> exit
| SW | GPDB | Down | 26 | gpdb 설치 경로 권한 설정 | cdw | [~]# all
=> chown -R gpadmin:gpadmin /usr/local/greenplum-db*
=> ls -al /usr/local ¦ grep greenplum
[rk9gs2] lrwxrwxrwx 1 gpadmin gpadmin 29 Aug 29 12:22 greenplum-db -> /usr/local/greenplum-db-7.5.2
[rk9gs2] drwxr-xr-x 11 gpadmin gpadmin 4096 Aug 29 12:22 greenplum-db-7.5.2
=> exit
| SW | OS | Down | 27 | gpadmin 계정 키교환(1/2) | cdw | (1) ssh key 생성
[5 empty] | (real hostname) |  | [~]# chown -R gpadmin:gpadmin /data
[~]# ls -al /data
…
drwxr-xr-x. 4 gpadmin gpadmin 4096 May 4 21:21 staging
[~]# /bin/su - gpadmin
[~]$ ssh-keygen -t rsa -b 4096
Generating public/private rsa key pair.
Enter file in which to save the key (/home/gpadmin/.ssh/id_rsa):
Created directory '/home/gpadmin/.ssh'.
Enter passphrase (empty for no passphrase):
Enter same passphrase again:
Your identification has been saved in /home/gpadmin/.ssh/id_rsa
Your public key has been saved in /home/gpadmin/.ssh/id_rsa.pub
(2) ssh key 교환(real hostname)
[~]$ cd /data/staging
[7 empty] | [~]$ sh sshkey_copy.sh hostfile |  | * GPDB 클러스터의 모든 노드 대상으로 접속 여부와 암호 입력 필요
/usr/bin/ssh-copy-id: INFO: Source of key(s) to be installed: "/home/gpadmin/.ssh/id_rsa.pub"
The authenticity of host 'rk9gc1 (172.16.142.121)' can't be established.
ED25519 key fingerprint is SHA256:JXyQxqho0ivTvY5EA+JXaN+fI9ZNwL4Jj1F7U8FZuLc.
This key is not known by any other names
Are you sure you want to continue connecting (yes/no/[fingerprint])? yes
/usr/bin/ssh-copy-id: INFO: attempting to log in with the new key(s), to filter out any that are already installed
/usr/bin/ssh-copy-id: INFO: 1 key(s) remain to be installed -- if you are prompted now it is to install the new keys
gpadmin@rk9gc1's password:
…
| SW | OS | Down | 28 | gpadmin 계정 키교환(2/2) | cdw | (1) ssh key 교환(alias hostname)
[5 empty] | (alias hostname) |  | [~]$ sh sshkey_copy.sh hostfile_alias |  | * GPDB 클러스터의 모든 노드 대상으로 접속 여부 입력 필요
/usr/bin/ssh-copy-id: INFO: Source of key(s) to be installed: "/home/gpadmin/.ssh/id_rsa.pub"
The authenticity of host 'cdw (172.16.142.121)' can't be established.
ED25519 key fingerprint is SHA256:JXyQxqho0ivTvY5EA+JXaN+fI9ZNwL4Jj1F7U8FZuLc.
Are you sure you want to continue connecting (yes/no/[fingerprint])? yes
/usr/bin/ssh-copy-id: INFO: attempting to log in with the new key(s), to filter out any that are already installed
/usr/bin/ssh-copy-id: WARNING: All keys were skipped because they already exist on the remote system.
(if you think this is a mistake, you may want to use -f option)
(2) gpssh 접속 여부 확인
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpssh -f /data/staging/hostfile
=> hostname
=> ls -al /home/gpadmin/.ssh
=> exit
[~]$ gpssh -f /data/staging/hostfile_alias
=> hostname
=> exit
| SW | OS | Down | 29 | gpssh-exkeys 실행 | cdw | (1) gpssh-exkeys 실행(hostname)
[5 empty] | (gpadmin 계정) |  | [~]$ gpssh-exkeys -f /data/staging/hostfile |  | * GPDB 클러스터의 모든 노드 대상으로 접속 여부 입력 필요
[STEP 1 of 5] create local ID and authorize on local host
... /home/gpadmin/.ssh/id_rsa file exists ... key generation skipped
[STEP 2 of 5] keyscan all hosts and update known_hosts file
[STEP 3 of 5] retrieving credentials from remote hosts
... send to rk9gc2
... send to rk9gs1
... send to rk9gs2
[STEP 4 of 5] determine common authentication file content
[STEP 5 of 5] copy authentication files to all remote hosts
... finished key exchange with rk9gc2
... finished key exchange with rk9gs1
... finished key exchange with rk9gs2
[INFO] completed successfully
(2) gpssh-exkeys 실행(alias hostname)
[~]$ gpssh-exkeys -f /data/staging/hostfile_alias
[STEP 1 of 5] create local ID and authorize on local host
... /home/gpadmin/.ssh/id_rsa file exists ... key generation skipped
[STEP 2 of 5] keyscan all hosts and update known_hosts file
[STEP 3 of 5] retrieving credentials from remote hosts
... send to scdw
... send to sdw1
... send to sdw2
[STEP 4 of 5] determine common authentication file content
[STEP 5 of 5] copy authentication files to all remote hosts
... finished key exchange with scdw
... finished key exchange with sdw1
... finished key exchange with sdw2
[INFO] completed successfully
| SW | OS | Down | 30 | gpssh-exkeys 실행 | cdw | [~]$ /bin/su -
[5 empty] | (root 계정) |  | (1) gpssh-exkeys 실행(hostname) |  | * GPDB 클러스터의 모든 노드 대상으로 접속 여부 입력 필요
[~]# gpssh-exkeys -f /data/staging/hostfile
[STEP 1 of 5] create local ID and authorize on local host
... /root/.ssh/id_rsa file exists ... key generation skipped
[STEP 2 of 5] keyscan all hosts and update known_hosts file
[STEP 3 of 5] retrieving credentials from remote hosts
... send to rk9gc2
... send to rk9gs1
... send to rk9gs2
[STEP 4 of 5] determine common authentication file content
[STEP 5 of 5] copy authentication files to all remote hosts
... finished key exchange with rk9gc2
... finished key exchange with rk9gs1
... finished key exchange with rk9gs2
[INFO] completed successfully
(2) gpssh-exkeys 실행(alias hostname)
[~]# gpssh-exkeys -f /data/staging/hostfile_alias
[STEP 1 of 5] create local ID and authorize on local host
... /root/.ssh/id_rsa file exists ... key generation skipped
[STEP 2 of 5] keyscan all hosts and update known_hosts file
[STEP 3 of 5] retrieving credentials from remote hosts
... send to scdw
... send to sdw1
... send to sdw2
[STEP 4 of 5] determine common authentication file content
[STEP 5 of 5] copy authentication files to all remote hosts
... finished key exchange with scdw
... finished key exchange with sdw1
... finished key exchange with sdw2
[INFO] completed successfully
| SW | GPDB | Down | 31 | gpadmin 계정 | cdw | (1) /etc/sudoers 파일 수정 |  | * /etc/sudoers 파일은 visudo 명령으로만 편집이 가능함
[5 empty] | sudo 권한 부여 설정 |  | [~]# visudo
[~]# cat /etc/sudoers ¦ grep "%wheel" ¦ grep -v "#"
%wheel ALL=(ALL) ALL
%wheel ALL=(ALL) NOPASSWD: ALL <<< 주석 제거
(2) /etc/sudoers 파일을 모든 cluster node에 복사
[~]# gpsync -f /data/staging/hostfile /etc/sudoers =:/etc/sudoers
[~]# all
=> cat /etc/sudoers ¦ egrep "%wheel" ¦ grep "NOPASSWD" ¦ grep -v "#"
[rk9gc2] %wheel ALL=(ALL) NOPASSWD: ALL
(3) wheel 그룹에 gpadmin 계정을 추가
=> usermod -aG wheel gpadmin
=> cat /etc/group ¦ grep wheel
[rk9gc2] wheel:x:10:gpadmin
=> exit
| SW | GPDB | Down | 32 | GPDB Directory 생성 | cdw | (1) cdw 에서 원격으로 수행 |  | * /data 폴더에 utilites, statlog 폴더는 설치 이후 GPDB 관리 스크립트 및 로그파일 저장 용도
[5 empty] | for coordinator |  | [~]# gpssh -h cdw -h scdw
=> hostname
=> mkdir -p /data/coordinator
=> mkdir -p /data/cores
=> mkdir -p /data/utilities
=> chown -R gpadmin:gpadmin /data/
=> ls -al /data/
[scdw] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:06 cores
[scdw] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:05 coordinator
[scdw] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:06 utilities
=> cd /home/gpadmin
=> ln -s /data/cores cores
=> ln -s /data/utilities utilities
=> chown -h gpadmin:gpadmin cores
=> chown -h gpadmin:gpadmin utilities
=> ls -al
…
[scdw] lrwxrwxrwx 1 gpadmin gpadmin 11 Jul 18 04:07 cores -> /data/cores
[scdw] lrwxrwxrwx 1 gpadmin gpadmin 15 Jul 18 04:07 utilities -> /data/utilities
=> exit
| SW | GPDB | Down | 33 | GPDB Directory 생성 | cdw | (1) cdw 에서 원격으로 수행 (data1, data2 filesystem 경로명에 따라 변경하여 수행) |  | * /data 폴더에 utilites, statlog 폴더는 설치 이후 GPDB 관리 스크립트 및 로그파일 저장 용도
[5 empty] | for Segment |  | [~]# seg
=> hostname
=> mkdir -p /data/primary
=> mkdir -p /data/mirror
=> mkdir -p /data/cores
=> mkdir -p /data/utilities
=> chown -R gpadmin:gpadmin /data/
=> ls -al /data/
[rk9gs4] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:10 cores
[rk9gs4] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:10 mirror
[rk9gs4] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:10 primary
[rk9gs4] drwxr-xr-x 2 gpadmin gpadmin 6 Jul 18 04:10 utilities
=> cd /home/gpadmin
=> ln -s /data/cores cores
=> ln -s /data/utilities utilities
=> chown -h gpadmin:gpadmin cores
=> chown -h gpadmin:gpadmin utilities
=> ls -al
…
[rk9gs4] lrwxrwxrwx 1 gpadmin gpadmin 11 Jul 18 04:11 cores -> /data/cores
[rk9gs4] lrwxrwxrwx 1 gpadmin gpadmin 15 Jul 18 04:11 utilities -> /data/utilities
=> exit
| SW | GPDB | Down | 34 | gpinitsystem 준비 | cdw | (1) gpconfigs 폴더 생성 및 hostfile 생성 (gpadmin 계정으로 수행) |  | * gpinitsystem_config 파일에서 coordinator hostname은 서버의 real host name을 사용해야 함
[~]$ /bin/su - gpadmin
[7 empty] | [~]$ mkdir /home/gpadmin/gpconfigs |  | * DATA_DIRECTORY 경로는 고객의 filesystem 및 segment node별 instance 갯수에 따라 설정 필요함
[~]$ cat /data/staging/hostfile > /home/gpadmin/gpconfigs/hostfile
[~]$ cat /data/staging/hostfile_alias > /home/gpadmin/gpconfigs/hostfile_alias
[~]$ cat /data/staging/hostfile_seg > /home/gpadmin/gpconfigs/hostfile_seg
[~]$ cat /data/staging/hostfile_seg_alias > /home/gpadmin/gpconfigs/hostfile_seg_alias
[~]$ ls -al /home/gpadmin/gpconfigs
-rw-r--r-- 1 gpadmin gpadmin 42 Jul 18 04:14 hostfile
-rw-r--r-- 1 gpadmin gpadmin 29 Jul 18 04:14 hostfile_alias
-rw-r--r-- 1 gpadmin gpadmin 28 Jul 18 04:14 hostfile_seg
-rw-r--r-- 1 gpadmin gpadmin 20 Jul 18 04:14 hostfile_seg_alias
(2) config file 복사
[~]$ cp /usr/local/greenplum-db/docs/cli_help/gpconfigs/gpinitsystem_config /home/gpadmin/gpconfigs/
(3) Config 설정
[~]$ vi /home/gpadmin/gpconfigs/gpinitsystem_config
[~]$ cat /home/gpadmin/gpconfigs/gpinitsystem_config ¦ grep -v "#"
ARRAY_NAME="Greenplum Data Platform"
SEG_PREFIX=gpseg
[8 empty] | PORT_BASE=6000 <<< 비고 설명 참조 | * PORT_BASE 설정 고려사항
[8 empty] | declare -a DATA_DIRECTORY=(/data/primary /data/primary) <<< 구성하는 instance 갯수에 맞게 변경 | net.ipv4.ip_local_port_range = 10000 65535인 경우 기본 포트 번호를 이 값으로 설정합니다.
[8 empty] | coordinator_HOSTNAME=rk9gc1 <<< 서버 real hostname 지정 | PORT_BASE = 6000
[8 empty] | coordinator_DIRECTORY=/data/coordinator | MIRROR_PORT_BASE = 7000
coordinator_PORT=5432
TRUSTED SHELL=ssh
CHECK_POINT_SEGMENTS=8
ENCODING=UNICODE
| SW | GPDB | Down | 35 | gpinitsystem 실행 | cdw | [~]$ cd /home/gpadmin/gpconfigs |  | * 고려사항 (sement node가 4대를 초과할 경우)
[7 empty] | [~]$ source /usr/local/greenplum-db/greenplum_path.sh |  | * segment node가 4대를 초과하는 경우 mirror instance spread 구성을 위해서 최초 gpinistsystem은 4대의 segment node를 대상으로 진행하고, segment hostfile도 별도로 생성(예 : hostfile_seg_init) 권고
[8 empty] | [~]$ cat ./hostfile_seg | * gpinitsystem을 실행하면 중간에 생성 여부에 대해서 입력하는 단계가 나오면 "Y" 또는 "y"를 입력
rk9gs1
rk9gs2
…
[~]$ gpinitsystem -c ./gpinitsystem_config -n C -h ./hostfile_seg
...
Continue with Greenplum creation Yy¦Nn (default=N):
> y
…
| SW | GPDB | Down | 36 | gpadmin 계정 환경변수 설정 | cdw | [~]$ vi ~/.bashrc |  | * 상세한 환경변수 설정 내용은 'bashrc' 시트를 참조
[8 empty] | [~]$ cat ~/.bashrc | * scdw 서버의 .bashrc과 동기화를 위해서 scp 명령으로 복사 필요함
##############################
### GPDB Environment Setting
##############################
source /usr/local/greenplum-db/greenplum_path.sh
export COORDINATOR_DATA_DIRECTORY=/data/coordinator/gpseg-1
export PGPORT=5432
...
[~]$ source ~/.bashrc
[~]$ scp /home/gpadmin/.bashrc scdw:/home/gpadmin/
| SW | GPDB | Down | 37 | 사용자 DB 생성 및 | cdw | (1) DB 생성 및 gpadmin DB계정 암호 설정
[5 empty] | gpadmin DB계정 암호 설정 |  | [~]$ createdb gpadmin
[~]$ psql -d gpadmin -c "alter user gpadmin password 'changeme';"
ALTER ROLE
[7 empty] | [~]$ psql -d gpadmin -c "create extension gp_toolkit;" |  | * 이미 생성되어 있는 경우 에러 메시지 발생 할 수 있음
[7 empty] | CREATE EXTENSION |  | ERROR: extension "gp_toolkit" already exists
(2) Timezone 설정 확인
[~]$ gpconfig -s TimeZone
Values on all segments are consistent
GUC : TimeZone
coordinator value: ROK
Segment value: ROK
[7 empty] | (3) Timezone 설정 (2번의 결과값이 올바르지 않은 경우 수행) |  | * TimeZone은 'ROK' 또는 'Asia/Seoul' 로 표기될 수 있음
[~]$ gpconfig -c TimeZone -v 'ROK'
20240718:04:26:33:019003 gpconfig:rk9gc1:gpadmin-[INFO]:-completed successfully with parameters '-c TimeZone -v ROK'
| SW | GPDB | Down | 38 | segment gpadmirror 수행 | cdw | (1) spread mirror 구성 할 수 있는 output 파일 생성 |  | * 고려사항 (sement node가 4대를 초과할 경우)
[7 empty] | [~]$ cd /home/gpadmin/gpconfigs |  | * segment node가 4대를 초과하는 경우 mirror instance spread 구성을 위해서 최초 gpinistsystem은 4대의 segment node를 대상으로 진행하고, segment hostfile도 별도로 생성(예 : hostfile_seg_init) 권고
[7 empty] | [~]$ gpaddmirrors -s -o addmirror_config |  | * gpinitsystem을 실행하면 중간에 생성 여부에 대해서 입력하는 단계가 나오면 "Y" 또는 "y"를 입력
…
20240718:04:30:16:019219 gpaddmirrors:rk9gc1:gpadmin-[INFO]:-Heap checksum setting consistent across cluster
Enter mirror segment data directory location 1 of 4 >
/data/mirror
Enter mirror segment data directory location 2 of 4 >
/data/mirror
Enter mirror segment data directory location 3 of 4 >
/data/mirror
Enter mirror segment data directory location 4 of 4 >
/data/mirror
20240718:04:31:23:019219 gpaddmirrors:rk9gc1:gpadmin-[INFO]:-Configuration file output to addmirror_config successfully.
(2) output 파일을 이용하여 gpaddmirror 수행 및 결과 확인
[~]$ gpaddmirrors -i addmirror_config
…
Continue with add mirrors procedure Yy¦Nn (default=N):
> y
...
[~]$ gpstate -m
| SW | GPDB | Down | 39 | gpexpand map file 생성 | cdw | (1) expand map file 생성하는 스크립트 수행 및 복사 |  | * sement node가 4대를 초과할 경우 수행
[5 empty] | (필요 시 수행) |  | [~]$ sh /data/staging/install_pkg/crt_expand_map_gp7.sh
[~]$ cp /data/staging/result_expand_map.out /home/gpadmin/gpconfigs/gpexpand_map
(2) 생성된 map file 내용 확인
[~]$ cat /home/gpadmin/gpconfigs/gpexpand_map
| SW | GPDB | Down | 40 | gpexpand 수행 | cdw | (1) gpexpand 대상 segment 명시한 hostfile 작성 |  | * sement node가 4대를 초과할 경우 수행
[5 empty] | (필요 시 수행) |  | [~]$ vi /home/gpadmin/gpconfigs/hostfile_seg_expand
[~]$ cat /home/gpadmin/gpconfigs/hostfile_seg_expand
rk9gs5
rk9gs6
…
(2) gpexpand 수행
[~]$ gpexpand -f /home/gpadmin/gpconfigs/hostfile_seg_expand -i /home/gpadmin/gpconfigs/gpexpand_map
(3) gpexpand 종료 후 작업용 schema 정리
[~]$ gpexpand -c
| SW | GPDB | Down | 41 | Standby coordinator 구성 | cdw | [~]$ gpinitstandby -s rk9gc2 |  | * scdw 서버의 real hostname을 사용해야 함
…
Do you want to continue with standby coordinator initialization? Yy¦Nn (default=N):
> y
...
[~]$ gpstate -f
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:-Starting gpstate with args: -f
…
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:-Standby coordinator details
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:-----------------------
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:- Standby address = rk9gc2
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:- Standby data directory = /data/coordinator/gpseg-1
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:- Standby port = 5432
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:- Standby PID = 9188
20240718:04:46:52:019601 gpstate:rk9gc1:gpadmin-[INFO]:- Standby status = Standby host passive
…
| SW | GPCC | Down | 42 | GPCC 설치 경로 설정 | cdw | [~]$ source /usr/local/greenplum-db/greenplum_path.sh |  | * /usr/local 경로의 권한을 임시로 777로 변경 후 gpcc 설치
[~]$ gpssh -f ~/gpconfigs/hostfile 'sudo chmod 777 /usr/local'
[~]$ gpssh -f ~/gpconfigs/hostfile 'sudo ls -al /usr ¦ grep local'
[rk9gs1] drwxrwxrwx. 13 root root 177 Mar 6 15:19 local
| SW | GPCC | Down | 43 | GPCC 환경설정 파일 작성 | cdw | [~]$ cd /home/gpadmin/gpconfigs |  | * Configuration File로 설치하기 위해서 Configuration File을 미리 생성
[7 empty] | [~]$ vi gpcc.conf |  | -> display_name, language 등의 항목 설정은 사용자 환경에 맞게 변경
[8 empty] | [~]$ cat gpcc.conf ¦ grep -v "#" | -> 설정파일 예제는 gpcc_conf sheet를 참조
path = /usr/local
display_name = rk9gc1
coordinator_port = 5432
web_port = 28080
rpc_port = 8899
enable_ssl = false
enable_kerberos = false
language = 1
[~]$ sed -i 's/display_name = gpadmin/display_name = '"$HOSTNAME"'/g' gpcc.conf
[~]$ cat gpcc.conf ¦ grep display_name
# Set the display_name param to the string to display in the GPCC UI.
display_name = rk9gc1
| SW | GPCC | Down | 44 | GPCC 설치 | cdw | [~]$ source /usr/local/greenplum-db/greenplum_path.sh |  | * gpadmin 계정으로 GPCC 설치하며, 미리 생성한 Configuration File로 설치
[~]$ cd /data/staging/gpdb752_rh9
[~]$ unzip greenplum-cc-web-7.4.0-gp7-el9-x86_64.zip
Archive: greenplum-cc-web-7.4.0-gp7-el9-x86_64.zip
creating: greenplum-cc-web-7.4.0-gp7-el9-x86_64/
inflating: greenplum-cc-web-7.4.0-gp7-el9-x86_64/gpccinstall-7.4.0
[~]$ cd greenplum-cc-web-7.4.0-gp7-el9-x86_64
[~]$ ./gpccinstall-7.4.0 -c /home/gpadmin/gpconfigs/gpcc.conf
…
INSTALLATION IN PROGRESS...
...
[7 empty] | CREATING SUPERUSER 'gpmon'... |  | -> 라이선스 동의를 위해서 라이선스 안내화면에서 'q' 키를 입력
CREATING COMMAND CENTER DATABASE 'gpperfmon'...
RELOADING pg_hba.conf. PLEASE WAIT ...
[7 empty] | … |  | -> 라이선스 동의 여부 확인 단계에서 기본값이 'Y' 이므로 엔터키 입력
| SW | GPCC | Down | 45 | GPCC 설치 확인 | cdw | [~]$ all |  | * GPCC 설치 후 /usr/local에 gpcc symbolic link 생성 여부 확인
[5 empty] | 경로 설정 원복 |  | => ls -al /usr/local ¦ grep greenplum |  | -> 생성되어있지 않다면 ln 명령으로 symbolic link 생성 필요
[rk9gs2] lrwxrwxrwx 1 gpadmin gpadmin 29 Aug 29 15:10 greenplum-cc -> /usr/local/greenplum-cc-7.4.0
[rk9gs2] drwxr-xr-x 11 gpadmin gpadmin 191 Aug 29 15:10 greenplum-cc-7.4.0
[rk9gs2] lrwxrwxrwx 1 gpadmin gpadmin 29 Aug 29 12:22 greenplum-db -> /usr/local/greenplum-db-7.5.2
[rk9gs2] drwxr-xr-x 11 gpadmin gpadmin 4096 Aug 29 12:22 greenplum-db-7.5.2
=> exit
[7 empty] | [~]$ gpssh -f ~/gpconfigs/hostfile 'sudo chmod 755 /usr/local' |  | * /usr/local 경로의 권한을 755로 복원
[~]$ gpssh -f ~/gpconfigs/hostfile 'sudo ls -al /usr ¦ grep local'
[rk9gc1] drwxr-xr-x. 15 root root 4096 Jul 18 05:15 local
| SW | GPCC | Down | 46 | GPCC 환경변수 설정 | cdw | [~]$ echo "source /usr/local/greenplum-cc/gpcc_path.sh" >> ~/.bashrc
[~]$ echo "export GPPERFMONHOME=/usr/local/greenplum-cc" >> ~/.bashrc
[~]$ cat ~/.bashrc ¦ grep "greenplum-cc"
source /usr/local/greenplum-cc/gpcc_path.sh
export GPPERFMONHOME=/usr/local/greenplum-cc
[~]$ source ~/.bashrc
[~]$ scp ~/.bashrc scdw:/home/gpadmin
| SW | GPCC | Down | 47 | GPCC 시작 | cdw | [~]$ gpcc status
2024-07-18 05:23:17 GPCC webserver: stopped
2024-07-18 05:23:18 GPCC agents: 0/6 agents running
[~]$ gpcc start
2025-08-14 17:11:02 Starting the gpcc agents and webserver...
2025-08-14 17:11:03 No need to migrate gpmetrics folder from /data/coordinator/gpseg-1/gpmetrics
2025-08-14 17:11:03 Starting GPCC 7.4.0 from /usr/local/greenplum-cc-7.4.0 ...
2025-08-14 17:11:06 Agent successfully started on 4/4 hosts
2025-08-14 17:11:06 View Greenplum Command Center at http://rk9gc1:28080
| SW | GPCC | Down | 48 | MetricsCollector 설치 | cdw | [~]$ cd /usr/local/greenplum-cc/gppkg
(1) GPDB 버전에 맞는 MetricsCollector 패키지 파일이 있는 경우
[~]$ ls -al
[~]$ gppkg -i MetricsCollector-6.13.1_gp_6.29.0-rhel9-x86_64.gppkg
(2) GPDB 버전에 맞는 MetricsCollector 패키지 파일이 없는 경우 설치 생략
[~]$ ls -al
| SW | GPCC | Down | 49 | GPCC 데이터 수집 설정 | cdw | (1) GPCC web 화면 로그인
[5 empty] | & GPCC 중지 |  | (2) [Admin] > [Settings] 메뉴 선택
(3) [Enable GPCC history data collection] 항목 ON 설정 및 확인
(4) GPCC 중지
[~]$ gpcc stop
| SW | GPPKG | Down | 50 | java path 확인 | cdw | [~]$ /bin/su - |  | * java 버전이 11.0.x 이상이고 설치 경로가 /usr/lib/jvm 아래인지 확인
[~]# all
=> alternatives --display java ¦ grep currently
[rk9gc1] link currently points to /usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64/bin/java
=> which java
[rk9gc1] /usr/bin/java
=> ls -al /usr/bin/java
[rk9gc1] lrwxrwxrwx. 1 root root 22 Jul 11 22:07 /usr/bin/java -> /etc/alternatives/java
=> exit
| SW | GPPKG | Down | 51 | root의 .bashrc | cdw | (1) cdw 서버의 .bashrc에 java_path 추가
[5 empty] | java path 설정 |  | [~]# echo "JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64/bin/java" >> ~/.bashrc
[~]# echo "export JAVA_HOME" >> ~/.bashrc
[~]# cat ~/.bashrc ¦ grep JAVA
JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.23.0.9-3.el9.x86_64/bin/java
export JAVA_HOME
[~]# source ~/.bashrc
[~]# java -version
openjdk version "11.0.25" 2024-10-15 LTS
OpenJDK Runtime Environment (Red_Hat-11.0.25.0.9-1) (build 11.0.25+9-LTS)
OpenJDK 64-Bit Server VM (Red_Hat-11.0.25.0.9-1) (build 11.0.25+9-LTS, mixed mode, sharing)
(2) .bashrc 파일을 모든 서버에 복사 및 결과 확인
[~]# gpsync -f /data/staging/hostfile /root/.bashrc =:/root/.bashrc
[~]# all
=> cat /root/.bashrc ¦ grep JAVA
[rk9gc2] JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64/bin/java
[rk9gc2] export JAVA_HOME
=> exit
| SW | GPPKG | Down | 52 | PL/Java 설치 (1/2) | cdw | [~]# /bin/su - gpadmin |  | * pl/java 설치 하면 greenplum_path.sh에 java 환경변수가 추가됨
[~]$ cd /data/staging/gpdb752_rh9
[~]$ gppkg install pljava-2.0.9-gp7-rhel9_x86_64.gppkg
Detecting network topology: [=============================] [OK]
2 coordinators and 8 segment instances are detected on 4 unique hosts.
Distributing package: [=============================] [OK]
Decoding package: [=============================] [OK]
Verifying package installation:[=============================] [OK]
Verifying package integrity: [=============================] [OK]
You are going to install the following packages:
Install 'pljava@2.0.9'
Continue? [y/N] y
Allocating disk space: [=============================] [OK]
Install 'pljava': [=============================] [OK]
Result:
pljava has been successfully installed
Clean Up: [=============================] [OK]
| SW | GPPKG | Down | 53 | gpadmin의 greenplum_path.sh | cdw | (1) cdw 서버의 greenplum_path.sh에 Java 환경설정 추가
[5 empty] | java path 변경 |  | [~]$ vi /usr/local/greenplum-db/greenplum_path.sh
[~]$ cat /usr/local/greenplum-db/greenplum_path.sh ¦ tail -n 4
### BEGIN EXTENSION PLJAVA
export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64
export LD_LIBRARY_PATH=$GPHOME/lib:$GPHOME/ext/python/lib:$JAVA_HOME/lib/server:$LD_LIBRARY_PATH
(2) greenplum_path.sh 파일을 모든 서버에 복사 및 결과 확인
[~]$ gpsync -f /data/staging/hostfile /usr/local/greenplum-db/greenplum_path.sh =:/usr/local/greenplum-db/greenplum_path.sh
[~]$ all
=> cat /usr/local/greenplum-db/greenplum_path.sh ¦ tail -n 4
[rk9gs2]
[rk9gs2] ### BEGIN EXTENSION PLJAVA
[rk9gs2] export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.23.0.9-3.el9.x86_64
[rk9gs2] export LD_LIBRARY_PATH=$GPHOME/lib:$GPHOME/ext/python/lib:$JAVA_HOME/lib/server:$LD_LIBRARY_PATH
=> exit
| SW | GPPKG | Down | 54 | PL/Java 설치 (2/2) | cdw | (1) gpdb 재시작
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -ra
(2) pl/java 등록 및 parameter change
[~]$ psql -d gpadmin -c "CREATE EXTENSION pljava;"
CREATE EXTENSION
[~]$ ls -al /usr/local/greenplum-db/lib/postgresql/java
[~]$ gpconfig -c pljava_classpath -v "pljava.jar:myclasses.jar"
20240718:06:02:48:028284 gpconfig:rk9gc1:gpadmin-[INFO]:-completed successfully with parameters '-c pljava_classpath -v pljava.jar:myclasses.jar'
[~]$ gpstop -u
[~]$ psql -f $GPHOME/share/postgresql/pljava/examples.sql
| SW | GPPKG | Down | 55 | PL/R 설치 | cdw | [~]$ cd /data/staging/gpdb752_rh9
[~]$ gppkg install plr-3.1.3-gp7-rhel9-x86_64.gppkg
Detecting network topology: [=============================] [OK]
2 coordinators and 8 segment instances are detected on 4 unique hosts.
Distributing package: [=============================] [OK]
Decoding package: [=============================] [OK]
Verifying package installation:[=============================] [OK]
Verifying package integrity: [=============================] [OK]
You are going to install the following packages:
Install 'plr@3.1.3-0'
Continue? [y/N] y
Allocating disk space: [=============================] [OK]
Install 'plr': [=============================] [OK]
Result:
plr has been successfully installed
Clean Up: [=============================] [OK]
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -ra
[~]$ psql -d gpadmin -c "CREATE EXTENSION plr;"
CREATE EXTENSION
| SW | GPPKG | Down | 56 | DS package 설치 | cdw | [~]$ cd /data/staging/gpdb752_rh9
[~]$ gppkg install DataSciencePython3.11-3.0.1-gp7-el9_x86_64.gppkg
Detecting network topology: [=============================] [OK]
2 coordinators and 8 segment instances are detected on 4 unique hosts.
Distributing package: [=============================] [OK]
Decoding package: [=============================] [OK]
Verifying package installation:[=============================] [OK]
Verifying package integrity: [=============================] [OK]
You are going to install the following packages:
Install 'DataSciencePython3.11@3.0.1'
Continue? [y/N] y
Allocating disk space: [=============================] [OK]
Install 'DataSciencePython3.11:[=============================] [OK]
The stdout from the script of the post-install: ] 0.0
==========================================================================
Please set GUC "plpython3.python_path" for plpython3 to find the libraries.
For example:
gpconfig -c plpython3.python_path \
-v "'$GPHOME/ext/DataSciencePython3.11/lib/python3.11/site-packages:$GPHOME/ext/DataSciencePython3.11/lib64/python3.11/site-packages'" \
--skipvalidation
gpstop -u
==========================================================================
Running post-install hook: [=============================] [OK]
Result:
DataSciencePython3.11 has been successfully installed
Clean Up: [=============================] [OK]
[7 empty] | [~]$ gpconfig -c plpython3.python_path -v "'$GPHOME/ext/DataSciencePython3.11/lib/python3.11/site-packages:$GPHOME/ext/DataSciencePython3.11/lib64/python3.11/site-packages'" --skipvalidation |  | * DataSciencePython3.x 설치 한 경우 파라메터 설정 필요
[~]$ gpstop -u
[~]$ gppkg install DataScienceR-2.2.0-gp7-el9_x86_64.gppkg
Detecting network topology: [=============================] [OK]
2 coordinators and 8 segment instances are detected on 4 unique hosts.
Distributing package: [=============================] [OK]
Decoding package: [=============================] [OK]
Verifying package installation:[=============================] [OK]
Verifying package integrity: [=============================] [OK]
You are going to install the following packages:
Install 'DataScienceR@2.2.0'
Continue? [y/N] y
Allocating disk space: [=============================] [OK]
Install 'DataScienceR': [=============================] [OK]
Result:
DataScienceR has been successfully installed
Clean Up: [=============================] [OK]
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -ra
| SW | GPPKG | Down | 57 | MADlib 설치 | cdw | [~]$ cd /data/staging/gpdb752_rh9
[~]$ tar xzf madlib-2.2.0-gp7-el9-x86_64.tar.gz
[~]$ cd madlib-2.2.0-gp7-el9-x86_64
[~]$ gppkg install madlib-2.2.0-gp7-el9-x86_64.gppkg.tar.gz
Detecting network topology: [=============================] [OK]
2 coordinators and 8 segment instances are detected on 4 unique hosts.
Distributing package: [=============================] [OK]
Decoding package: [=============================] [OK]
Verifying package installation:[=============================] [OK]
Verifying package integrity: [=============================] [OK]
You are going to install the following packages:
Install 'madlib@2.2.0-gp7'
Continue? [y/N] y
Allocating disk space: [=============================] [OK]
Install 'madlib': [=============================] [OK]
The stdout from the script of the post-install: ] 0.0
Please run the following command to deploy MADlib
CREATE EXTENSION madlib CASCADE;
Running post-install hook: [=============================] [OK]
Result:
madlib has been successfully installed
Clean Up: [=============================] [OK]
[~]$ psql -c "CREATE EXTENSION madlib CASCADE;"
NOTICE: installing required extension "plpython3u"
CREATE EXTENSION
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -ra
[~]$ gpstop -af
| SW | GPDB | Down | 58 | cgroup 구성 | cdw | (1) cgroup 버전 확인 및 cgroup-v2 마운트 설정(노드 재시작 포함) |  | * cgroup 버전 별 설정값 : v1 = tempfs, v2 = cgroup2fs
[7 empty] | [~]$ /bin/su - |  | * cgroup v2는 Greenplum v7 부터 지원하며, IO_LIMIT 기능을 지원함
[~]# all
=> stat -fc %T /sys/fs/cgroup/
[rk9gc2] cgroup2fs
=> grubby --update-kernel=ALL --args="systemd.unified_cgroup_hierarchy=1"
=> exit
[~]# seg
=> sync;sync;sync
=> init 6
=> exit
[~]# ssh scdw
[~]# sync;sync;sync
[~]# init 6
Connection to scdw closed.
[~]# sync;sync;sync
[~]# init 6
(2) cgroup 컨트롤러 생성
[~]# all
=> uptime
[rk9gs1] 10:56:21 up 3 min, 1 user, load average: 0.19, 0.10, 0.04
=> mkdir -p /sys/fs/cgroup/gpdb.service
=> echo "+cpuset +io +cpu +memory" ¦ tee -a /sys/fs/cgroup/cgroup.subtree_control
[rk9gs1] +cpuset +io +cpu +memory
=> chown -R gpadmin:gpadmin /sys/fs/cgroup/gpdb.service
=> chmod a+w /sys/fs/cgroup/cgroup.procs
=> exit
(3) cgroup 자동시작 설정 파일 작성 및 배포
[~]# vi /etc/systemd/system/gpdb.service
[~]# cat /etc/systemd/system/gpdb.service
[Unit]
Description=Greenplum Cgroup v2 Configuration Service
[Service]
Type=simple
WorkingDirectory=/sys/fs/cgroup/gpdb.service
Delegate=yes
Slice=-.slice
# set hierarchies only if cgroup v2 mounted
ExecCondition=bash -c '[ xcgroup2fs = x$(stat -fc "%%T" /sys/fs/cgroup) ] ¦¦ exit 1'
ExecStartPre=bash -ec " \
chown -R gpadmin:gpadmin .; \
chmod a+w ../cgroup.procs; \
mkdir -p helper.scope"
ExecStart=sleep infinity
ExecStartPost=bash -ec "echo $MAINPID > /sys/fs/cgroup/cgroup.procs;"
[Install]
WantedBy=basic.target
[~]# gpsync -f /data/staging/hostfile /etc/systemd/system/gpdb.service =:/etc/systemd/system/gpdb.service
(4) gpdb.service 데몬 활성화
[~]# all
=> systemctl daemon-reload
=> systemctl enable gpdb.service
[rk9gc2] Created symlink /etc/systemd/system/basic.target.wants/gpdb.service → /etc/systemd/system/gpdb.service.
=> systemctl status gpdb.service
[rk9gc2] ○ gpdb.service - Greenplum Cgroup v2 Configuration Service
[rk9gc2] Loaded: loaded (/etc/systemd/system/gpdb.service; enabled; preset: disabled)
[rk9gc2] Active: inactive (dead)
=> exit
(3) PSI(Pressure Stall Information) 활성화
[~]# all
=> grubby --update-kernel=ALL --args="psi=1"
=> exit
[~]# seg
=> sync;sync;sync
=> init 6
=> exit
[~]# ssh scdw
[~]# sync;sync;sync
[~]# init 6
Connection to scdw closed.
[~]# sync;sync;sync
[~]# init 6
| SW | GPDB | Down | 59 | cgroup 활성화 | cdw | (1) 재기동 여부 확인 |  | * cgroup 버전 별 설정값 : v1 = tempfs, v2 = cgroup2fs
[7 empty] | [~]# all |  | * cgroup v2는 Greenplum v7 부터 지원하며, IO_LIMIT 기능을 지원함
=> uptime
[rk9gs1] 11:16:14 up 1 min, 1 user, load average: 0.18, 0.13, 0.05
=> exit
(2) GPDB 시작
[~]# /bin/su - gpadmin
Last login: Tue Aug 19 21:56:19 KST 2025 on pts/0
[~]$ gpstart -a
…
20250822:11:16:31:001412 gpstart:rk9gc1:gpadmin-[INFO]:-Database successfully started
(3) cgroup 파라메터 설정 및 적용
[~]$ gpconfig -c gp_resource_manager -v "group-v2"
20250822:11:19:03:001992 gpconfig:rk9gc1:gpadmin-[INFO]:-completed successfully with parameters '-c gp_resource_manager -v group-v2'
[~]$ gpstop -ra
…
20250822:11:19:45:002185 gpstop:rk9gc1:gpadmin-[INFO]:-Restarting System...
[~]$ gpconfig -s gp_resource_manager
Values on all segments are consistent
GUC : gp_resource_manager
Coordinator value: group-v2
Segment value: group-v2
| SW | GPDB | Down | 60 | gpconfig 설정 | cdw | [~]$ cd ~/gpconfigs
[5 empty] | GPDB & GPCC 재시작 |  | [~]$ vi gpconfigs_set.sh |  | * gpconfigs_set.sh 및 gpconfigs_chk.sh 파일 상세 내용은 'gpconfig' sheet를 참조하여 생성
[~]$ sh gpconfigs_set.sh
20250822:11:27:08:003482 gpconfig:rk9gc1:gpadmin-[INFO]:-completed successfully with parameters '-c gp_workfile_compression -v on --masteronly'
…
[~]$ gpstop -ra
…
20250822:11:28:04:004152 gpstop:rk9gc1:gpadmin-[INFO]:-Restarting System...
[~]$ gpcc start
2025-08-29 20:12:20 Starting the gpcc agents and webserver...
2025-08-29 20:12:21 redundant host rk9gc1 in cmds
2025-08-29 20:12:21 Starting GPCC 7.4.0 from /usr/local/greenplum-cc-7.4.0 ...
2025-08-29 20:12:27 Agent successfully started on 4/4 hosts
2025-08-29 20:12:27 View Greenplum Command Center at http://rk9gc1:28080
[~]$ vi gpconfigs_chk.sh
[~]$ sh gpconfigs_chk.sh
Values on all segments are consistent
GUC : gp_vmem_protect_limit
Coordinator value: 8192
Segment value: 8192
…
| SW | GPDB | Down | 61 | GPDB & GPCC 확인 | cdw | [~]$ gpstate
[~]$ gpstate -f
[~]$ gpstate -m
[~]$ gpstate -e
[~]$ gpcc status
| SW | GPDB | Down | 62 | gpadmin의 .bashrc | cdw | [~]$ all
[5 empty] | java path 설정 |  | => echo 'export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64' >> /home/gpadmin/.bashrc
=> cat /home/gpadmin/.bashrc ¦ grep JAVA_HOME
[rk9gs1] export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64
=> exit
| SW | PXF | Down | 63 | pxf 설치파일 배포 | cdw | [~]$ /bin/su -
[~]# cd /data/staging/gpdb752_rh9/
[~]# gpsync -f /home/gpadmin/gpconfigs/hostfile pxf-gp7-7.0.0-2.el9.x86_64.rpm =:/home/gpadmin/pxf-gp7-7.0.0-2.el9.x86_64.rpm
[~]# all
=> chown gpadmin:gpadmin /home/gpadmin/pxf-gp7-7.0.0-2.el9.x86_64.rpm
=> ls -al /home/gpadmin/pxf-gp7-*.rpm
[rk9gs2] -rw-r--r-- 1 gpadmin gpadmin 157962580 Aug 22 11:37 /home/gpadmin/pxf-gp7-7.0.0-2.el9.x86_64.rpm
=> exit
| SW | PXF | Down | 64 | pxf install | cdw | [~]# all
=> yum clean all
[rk9gs2] 41 files removed
=> yum repolist
[rk9gs2] repo id repo name
[rk9gs2] appstream Rocky Linux 9 - AppStream
[rk9gs2] baseos Rocky Linux 9 - BaseOS
[rk9gs2] epel Extra Packages for Enterprise Linux 9 - x86_64
[rk9gs2] epel-cisco-openh264 Extra Packages for Enterprise Linux 9 openh264 (From Cisco) - x86_64
[rk9gs2] extras Rocky Linux 9 - Extras
=> rpm -Uvh /home/gpadmin/pxf-gp7-7.0.0-2.el9.x86_64.rpm
[rk9gs2] Verifying... ################################# [100%]
[rk9gs2] Preparing... ################################# [100%]
[rk9gs2] Updating / installing...
[rk9gs2] 1:pxf-gp7-7.0.0-2.el9 ################################# [100%]
=> chown -R gpadmin:gpadmin /usr/local/pxf-gp*
=> ls -al /usr/local ¦ grep pxf-gp
[rk9gs2] drwxr-xr-x 8 gpadmin gpadmin 159 Aug 22 12:07 pxf-gp7
=> exit
| SW | PXF | Down | 65 | gpadmin의 .bashrc | cdw | [~]# /bin/su - gpadmin
[5 empty] | pxf 설정 |  | [~]$ all
=> echo 'export PATH=$PATH:/usr/local/pxf-gp7/bin' >> /home/gpadmin/.bashrc
=> cat /home/gpadmin/.bashrc ¦ grep -i pxf
[rk9gs1] export PATH=$PATH:/usr/local/pxf-gp7/bin
=> exit
| SW | PXF | Down | 66 | pxf 초기화 | cdw | [~]$ source ~/.bashrc
(1) pxf 파라메터를 template 파일에 설정
[7 empty] | [~]$ echo 'export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64' >> /usr/local/pxf-gp7/templates/conf/pxf-env.sh |  | * JAVA_HOME 설정(template 파일에 설정)
[7 empty] | [~]$ echo 'export PXF_JVM_OPTS="-Xmx3g -Xms1g"' >> /usr/local/pxf-gp7/templates/conf/pxf-env.sh |  | * PXF JVM memory 설정(template 파일에 설정)
[~]$ cat /usr/local/pxf-gp7/templates/conf/pxf-env.sh ¦ egrep 'JAVA_HOME¦PXF_JVM_OPTS' ¦ grep -v "#"
export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64
export PXF_JVM_OPTS="-Xmx3g -Xms1g"
(2) pxf 초기화
[~]$ pxf cluster prepare
Preparing PXF on coordinator host...
PXF prepared successfully on 1 out of 1 hosts
[~]$ pxf cluster register
Installing PXF extension on coordinator host, standby coordinator host, and 2 segment hosts...
PXF extension has been installed on 4 out of 4 hosts
Setting Greenplum configuration parameter 'pxf.pxf_base' on coordinator host...
Greenplum configuration parameter 'pxf.pxf_base' has been set on 1 out of 1 hosts
[~]$ cat /usr/local/pxf-gp7/clusters/default/groups/default/conf/pxf-env.sh ¦ grep -v "#"
| SW | PXF | Down | 67 | pxf 기동 및 확인 | cdw | [~]$ source ~/.bashrc
[~]$ pxf cluster sync
Checking PXF cluster directory is ready for the sync operation on standby coordinator host and 2 segment hosts...
PXF cluster directory is ready for the sync operation on 3 out of 3 hosts
Syncing PXF configuration files from coordinator host to standby coordinator host and 2 segment hosts...
PXF configs synced successfully on 3 out of 3 hosts
[~]$ pxf cluster start
Starting PXF on coordinator host, standby coordinator host, and 2 segment hosts...
PXF started successfully on 4 out of 4 hosts
[~]$ pxf cluster status
Checking status of PXF servers on coordinator host, standby coordinator host, and 2 segment hosts...
PXF is running on 4 out of 4 hosts
[7 empty] | [~]$ all |  | * PXF 초기 설정(template) 이후의 파라메터 설정은 아래 파일을 이용
[7 empty] | => cat /usr/local/pxf-gp7/clusters/default/groups/default/conf/pxf-env.sh ¦ grep -v "#" |  | * 파일 : /usr/local/pxf-gp7/clusters/default/groups/default/conf/pxf-env.sh
[rk9gs2] export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64
[rk9gs2] export PXF_JVM_OPTS="-Xmx3g -Xms1g"
| SW | PXF | Down | 68 | pxf 권한 부여 | cdw | [~]$ psql -c "CREATE EXTENSION pxf;"
CREATE EXTENSION
[~]$ psql -c "select * from pg_available_extensions where name = 'pxf';"
name ¦ default_version ¦ installed_version ¦ comment
------+-----------------+-------------------+-------------------------------------------------
pxf ¦ 3.0 ¦ 3.0 ¦ Extension which allows to access unmanaged data
(1 row)
[~]$ psql -c "GRANT all ON PROTOCOL pxf TO public;"
GRANT
| SW | GPDB | Down | 69 | GPDB 설치 결과 체크 | cdw | [~]$ cd /data/staging/install_pkg
[~]$ cat /home/gpadmin/gpconfigs/hostfile_alias ¦ grep cdw > /home/gpadmin/gpconfigs/hostfile_cdw
[~]$ sudo sh gpdb7_install_result_check.sh > gpdb7_install_result_check.log
| SW | GPDB | Down | 70 | core dump 자동생성 설정 | cdw | (1) disable of core file limit
[~]$ /bin/su -
[~]# echo 'DefaultLimitCORE=infinity' >> /etc/systemd/system.conf
[~]# cat /etc/systemd/system.conf ¦ grep -v "#"
[Manager]
DefaultLimitCORE=infinity
(2) system.conf 파일 배포
[~]# gpsync -f /home/gpadmin/gpconfigs/hostfile /etc/systemd/system.conf =:/etc/systemd/system.conf
[~]# all
=> cat /etc/systemd/system.conf ¦ grep DefaultLimitCORE
[rk9gc2] #DefaultLimitCORE=
[rk9gc2] DefaultLimitCORE=infinity
(3) systemd manager 재실행
=> systemctl daemon-reexec
=> ulimit -a ¦ grep core
[r9gs2] core file size (blocks, -c) unlimited
[r9gs1] core file size (blocks, -c) unlimited
[r9gm1] core file size (blocks, -c) unlimited
[r9gm2] core file size (blocks, -c) unlimited
=> exit
(4) core file 생성 테스트(테스트용 프로세스는 사용자가 임의로 수행 필요함)
[~]# kill -11 2827
[1] 2827
[~]# kill -11 2827
[~]#
[1]+ Segmentation fault (core dumped) sleep 100
[~]#
[~]# cd /data/cores/
[~]# ls -al
total 236
drwxr-xr-x 2 gpadmin gpadmin 47 Aug 21 16:50 .
drwxr-xr-x. 6 gpadmin gpadmin 65 Jul 18 04:06 ..
-rw------- 1 root root 442368 Aug 21 16:50 core-sleep-11-0-0-2827-1724284226
| SW | GPDB | Down | 71 | gpkrutil 설치 및 환경설정 | cdw | (1) gpkrutil 설치 |  | * gpkrutil은 Greenplum 운영 스크립트로써 github에서 다운로드 가능
[7 empty] | [~]$ ls -al /data/staging/install_pkg/gpkrutil-main.zip |  | * URL - https://github.com/gpdbkr/gpkrutil/tree/main
[7 empty] | -rw-r--r-- 1 gpadmin gpadmin 411256 Aug 29 20:46 /data/staging/install_pkg/gpkrutil-main.zip |  | * 다운로드 받은 gpkrutil 설치 파일은 /data/staging/install_pkg 폴더에 업로드
[~]$ cp /data/staging/install_pkg/gpkrutil-main.zip /data/gpkrutil-main.zip
[~]$ cd /data/
[~]$ unzip gpkrutil-main.zip
Archive: gpkrutil-main.zip
27b391127a70545c8e396c1cc04be80464a6bc09
creating: gpkrutil-main/
…
[~]$ mv gpkrutil-main gpkrutil
[~]$ cd gpkrutil
[~]$ ls -al
drwxr-xr-x 2 gpadmin gpadmin 126 Aug 27 10:50 backupconf
drwxr-xr-x 2 gpadmin gpadmin 4096 Aug 27 10:50 cronlog
drwxr-xr-x 2 gpadmin gpadmin 4096 Aug 27 10:50 crontool
…
(2) gpadmin 계정 PATH 설정 및 적용
[~]$ echo "" >> ~/.bashrc
[~]$ echo "### GPKRUTIL setup" >> ~/.bashrc
[~]$ echo "source /data/gpkrutil/gpkrutil_path.sh.gp7" >> ~/.bashrc
[~]$ tail -n 5 ~/.bashrc
export JAVA_HOME=/usr/lib/jvm/java-11-openjdk-11.0.25.0.9-7.el9.x86_64
export PATH=$PATH:/usr/local/pxf-gp7/bin
### GPKRUTIL setup
source /data/gpkrutil/gpkrutil_path.sh.gp7
[~]$ source ~/.bashrc
(3) hostfile 수정(사용자 환경에 맞게 변경 필요)
[~]$ cd $GPKRUTIL
[~]$ vi hostfile_all
[~]$ cat hostfile_all
cdw
scdw
sdw1
sdw2
…
[~]$ vi hostfile_seg
[~]$ cat hostfile_seg
sdw1
sdw2
…
| SW | GPDB | Down | 72 | gpkrutil 사용설정 | cdw | (1) gpkrutil용 table 및 view 생성 |  | * gpkrutil은 Greenplum 운영 스크립트로써 github에서 다운로드 가능
[7 empty] | [~]$ sh gpkrutil_crt_dba_schema.sh |  | * URL - https://github.com/gpdbkr/gpkrutil/tree/main
[7 empty] | [~]$ cat ./mnglog/gpkrutil_crt_dba_schema.log |  | * 다운로드 받은 gpkrutil 설치 파일은 /data/staging/install_pkg 폴더에 업로드
CREATE SCHEMA
CREATE TABLE
…
(2) meminfo 설정
[~]$ cd $GPKRUTIL/stattool
[~]$ cp setup_mem_info.sh setup_mem_info.sh.gp7
[~]$ sed -i 's/gpscp/gpsync/g' setup_mem_info.sh.gp7
[~]$ sh setup_mem_info.sh.gp7
Make /home/gpadmin/memutil/ to all nodes
…
Copy mem_info.sh to all segments
(3) crontab 설정
[~]$ cd $GPKRUTIL/crontool
[~]$ crontab crontab.txt
[~]$ crontab -l
## system resource logging
* * * * * /bin/bash /data/gpkrutil/crontool/cron_sys_rsc.sh 5 11 &
…
(4) log 생성여부 확인
[~]$ cd $GPKRUTIL/statlog
[~]$ ls -altr
…
-rw-r--r-- 1 gpadmin gpadmin 522 Aug 29 21:30 lt.20250829.txt
-rw-r--r-- 1 gpadmin gpadmin 90 Aug 29 21:30 session_user.20250829.txt
-rw-r--r-- 1 gpadmin gpadmin 19872 Aug 29 21:30 sys.20250829.txt
[~]$ cd $GPKRUTIL/cronlog
[~]$ ls -altr
…
-rw-r--r-- 1 gpadmin gpadmin 0 Aug 29 21:28 killed_idle.20250829.log
(5) alias 적용여부 확인
[~]$ qq
datname ¦ duration_time ¦ usename ¦ client_addr ¦ wait_event ¦ wait_event_type ¦ pid ¦ sess_id ¦ rsgname
-----------+-----------------+---------+----------------+-----------------+-----------------+-------+---------+-------------
gpperfmon ¦ 00:00:00.055949 ¦ gpmon ¦ 172.16.142.121 ¦ Dispatch/Result ¦ IPC ¦ 16405 ¦ 2803 ¦ admin_group
(1 row)
| SW | GPDB | Up | 73 | gpfailover 환경설정 | cdw | [~]$ /bin/su -
[~]# cd /data/staging/install_pkg/
[~]# tar -xzvf gpfailover_setup_gp7.tar.gz
[~]# cd /data/staging/install_pkg/bin/
[~]# chmod +x *
[~]# vi vip_env.sh
[~]# cat vip_env.sh
[8 empty] | GPMDW=cdw | <<< CDW 호스트네임
[8 empty] | GPSMDW=scdw | <<< SCDW 호스트네임
[8 empty] | ARPING_INTERFACE=ens160 | <<< 외부접속 이더넷 인터페이스 (Physical)
[8 empty] | VIP_INTERFACE=ens160:0 | <<< 외부접속 이더넷 인터페이스 (VIP)
[8 empty] | VIP=172.16.142.120 | <<< Virtual IP Address
[8 empty] | VIP_GW=172.16.142.2 | <<< Virtual IP Gateway
[8 empty] | VIP_NETMASK=255.255.252.0 | <<< Virtual IP Netmask
| SW | GPDB | Up | 74 | gpfailover daemon 설치 | cdw | [~]# sh setup_gpfo_rhel9_gp7.sh |  | * RHEL 6 버전은 setup_gpfo_rhel6.sh 파일 실행
Is current GPDB started?
vip_env.sh modified? y
mkdir: cannot create directory ‘/usr/local/bin’: File exists
1. Copy Files - cdw : OK
mkdir: cannot create directory ‘/usr/local/bin’: File exists
gpfailover.sh 100% 2932 3.0MB/s 00:00
gpfailovershutdown.sh 100% 99 106.6KB/s 00:00
setup_gpfo_rhel6.sh 100% 1756 2.4MB/s 00:00
setup_gpfo_rhel7.sh 100% 1988 2.3MB/s 00:00
setup_gpfo_rhel9_gp7.sh 100% 2071 3.1MB/s 00:00
vip_env.sh 100% 134 227.9KB/s 00:00
vip_start.sh 100% 187 316.6KB/s 00:00
vip_stop.sh 100% 91 136.9KB/s 00:00
vip 100% 493 574.2KB/s 00:00
gpfailover 100% 837 1.1MB/s 00:00
gpfailover.service 100% 181 211.5KB/s 00:00
gpfailover.service 100% 181 238.0KB/s 00:00
2. Copy Files - scdw : OK
ARPING 172.16.142.2 from 172.16.142.120 ens160
Unicast reply from 172.16.142.2 [00:50:56:F8:4B:7E] 0.762ms
Sent 1 probes (1 broadcast(s))
Received 1 response(s)
4. cdw vip_start : OK
active
● gpfailover.service - GPDB failover
Loaded: loaded (/etc/systemd/system/gpfailover.service; disabled; preset: disabled)
Active: active (running) since Thu 2025-08-28 08:12:29 KST; 397ms ago
Process: 12684 ExecStart=/etc/rc.d/init.d/gpfailover start (code=exited, status=0/SUCCESS)
Main PID: 12685 (gpfailover.sh)
Tasks: 5 (limit: 22932)
Memory: 2.5M
CPU: 235ms
CGroup: /system.slice/gpfailover.service
├─12685 bin/bash /usr/local/bin/gpfailover.sh
├─12724 bin/bash /usr/local/bin/gpfailover.sh
├─12725 ping -c 3 -i 3 cdw
├─12726 grep ", 0% packet loss"
└─12727 wc -l
Aug 28 08:12:29 rk9gc2 systemd[1]: Starting GPDB failover...
Aug 28 08:12:29 rk9gc2 greenplum-path.sh[12695]: loading environment from /usr/local/greenplum-db-7.5.2/etc/environment.d/25-data-science-R.conf
Aug 28 08:12:29 rk9gc2 greenplum-path.sh[12696]: loading environment from /usr/local/greenplum-db-7.5.2/etc/environment.d/30-pljava.conf
Aug 28 08:12:29 rk9gc2 greenplum-path.sh[12697]: loading environment from /usr/local/greenplum-db-7.5.2/etc/environment.d/30-plr.conf
Aug 28 08:12:29 rk9gc2 gpfailover[12684]: Starting GPDB Auto failover Daemon:
Aug 28 08:12:29 rk9gc2 gpfailover[12709]: gpfailover daemon is running
Aug 28 08:12:29 rk9gc2 systemd[1]: Started GPDB failover.
Synchronizing state of gpfailover.service with SysV service script with /usr/lib/systemd/systemd-sysv-install.
Executing: /usr/lib/systemd/systemd-sysv-install enable gpfailover
Failed to execute /usr/lib/systemd/systemd-sysv-install: No such file or directory
5. scdw service : OK
| SW | GPDB | Up | 75 | VIP 확인 | cdw | [~]# ifconfig -a
ens160: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 1500
inet 172.16.142.121 netmask 255.255.255.0 broadcast 172.16.142.255
inet6 fe80::20c:29ff:febb:6cf4 prefixlen 64 scopeid 0x20<link>
ether 00:0c:29:bb:6c:f4 txqueuelen 1000 (Ethernet)
RX packets 13775218 bytes 4659700312 (4.3 GiB)
RX errors 0 dropped 0 overruns 0 frame 0
TX packets 15091310 bytes 6993171889 (6.5 GiB)
TX errors 0 dropped 0 overruns 0 carrier 0 collisions 0
ens160:0: flags=4163<UP,BROADCAST,RUNNING,MULTICAST> mtu 1500
inet 172.16.142.120 netmask 255.255.252.0 broadcast 172.16.143.255
ether 00:0c:29:bb:6c:f4 txqueuelen 1000 (Ethernet)
| SW | GPDB | Up | 76 | Daemon 실행 확인 | scdw | [~]# ssh scdw
[~]# systemctl is-active gpfailover
active
[~]# systemctl status gpfailover
● gpfailover.service - GPDB failover
Loaded: loaded (/etc/systemd/system/gpfailover.service; disabled; preset: disabled)
Active: active (running) since Fri 2025-08-29 21:43:44 KST; 40s ago
Process: 5417 ExecStart=/etc/rc.d/init.d/gpfailover start (code=exited, status=0/SUCCESS)
Main PID: 5418 (gpfailover.sh)
Tasks: 2 (limit: 22933)
Memory: 2.1M
CPU: 436ms
CGroup: /system.slice/gpfailover.service
├─5418 bin/bash /usr/local/bin/gpfailover.sh
└─5582 sleep 5
Aug 29 21:43:44 rk9gc2 systemd[1]: Starting GPDB failover...
Aug 29 21:43:44 rk9gc2 greenplum-path.sh[5430]: loading environment from /usr/local/greenplum-db-7.5.2/etc/environment.d/30-plr.conf
Aug 29 21:43:44 rk9gc2 gpfailover[5417]: Starting GPDB Auto failover Daemon:
Aug 29 21:43:44 rk9gc2 gpfailover[5442]: gpfailover daemon is running
Aug 29 21:43:44 rk9gc2 systemd[1]: Started GPDB failover.

## set_sysctl
[~]# cat /root/set_sysctl_more64.sh | [~]# cat /root/set_sysctl_less64.sh
echo "" >> /etc/sysctl.conf | echo "" >> /etc/sysctl.conf
echo "kernel.shmall = "$(expr $(getconf _PHYS_PAGES) / 2) >> /etc/sysctl.conf | echo "kernel.shmall = "$(expr $(getconf _PHYS_PAGES) / 2) >> /etc/sysctl.conf
echo "kernel.shmmax = "$(expr $(getconf _PHYS_PAGES) / 2 \* $(getconf PAGE_SIZE)) >> /etc/sysctl.conf | echo "kernel.shmmax = "$(expr $(getconf _PHYS_PAGES) / 2 \* $(getconf PAGE_SIZE)) >> /etc/sysctl.conf
echo "kernel.shmmni = 32768" >> /etc/sysctl.conf | echo "kernel.shmmni = 32768" >> /etc/sysctl.conf
echo "vm.overcommit_memory = 2" >> /etc/sysctl.conf | echo "vm.overcommit_memory = 2" >> /etc/sysctl.conf
echo "vm.overcommit_ratio = 95" >> /etc/sysctl.conf | echo "vm.overcommit_ratio = 95" >> /etc/sysctl.conf
echo "net.ipv4.ip_local_port_range = 10000 65535" >> /etc/sysctl.conf | echo "net.ipv4.ip_local_port_range = 10000 65535" >> /etc/sysctl.conf
echo "kernel.sem = 32000 1048576000 1000 32768" >> /etc/sysctl.conf | echo "kernel.sem = 32000 1048576000 1000 32768" >> /etc/sysctl.conf
echo "kernel.sysrq = 1" >> /etc/sysctl.conf | echo "kernel.sysrq = 1" >> /etc/sysctl.conf
echo "kernel.core_uses_pid = 1" >> /etc/sysctl.conf | echo "kernel.core_uses_pid = 1" >> /etc/sysctl.conf
echo "kernel.msgmnb = 65536" >> /etc/sysctl.conf | echo "kernel.msgmnb = 65536" >> /etc/sysctl.conf
echo "kernel.msgmax = 65536" >> /etc/sysctl.conf | echo "kernel.msgmax = 65536" >> /etc/sysctl.conf
echo "kernel.msgmni = 32768" >> /etc/sysctl.conf | echo "kernel.msgmni = 32768" >> /etc/sysctl.conf
echo "net.ipv4.tcp_syncookies = 1" >> /etc/sysctl.conf | echo "net.ipv4.tcp_syncookies = 1" >> /etc/sysctl.conf
echo "net.ipv4.conf.default.accept_source_route = 0" >> /etc/sysctl.conf | echo "net.ipv4.conf.default.accept_source_route = 0" >> /etc/sysctl.conf
echo "net.ipv4.tcp_max_syn_backlog = 4096" >> /etc/sysctl.conf | echo "net.ipv4.tcp_max_syn_backlog = 4096" >> /etc/sysctl.conf
echo "net.ipv4.conf.all.arp_filter = 1" >> /etc/sysctl.conf | echo "net.ipv4.conf.all.arp_filter = 1" >> /etc/sysctl.conf
echo "net.ipv4.ipfrag_high_thresh = 41943040" >> /etc/sysctl.conf | echo "net.ipv4.ipfrag_high_thresh = 41943040" >> /etc/sysctl.conf
echo "net.ipv4.ipfrag_low_thresh = 31457280" >> /etc/sysctl.conf | echo "net.ipv4.ipfrag_low_thresh = 31457280" >> /etc/sysctl.conf
echo "net.ipv4.ipfrag_time = 60" >> /etc/sysctl.conf | echo "net.ipv4.ipfrag_time = 60" >> /etc/sysctl.conf
echo "net.core.netdev_max_backlog = 10000" >> /etc/sysctl.conf | echo "net.core.netdev_max_backlog = 10000" >> /etc/sysctl.conf
echo "net.core.rmem_max = 16777216" >> /etc/sysctl.conf | echo "net.core.rmem_max = 16777216" >> /etc/sysctl.conf
echo "net.core.wmem_max = 16777216" >> /etc/sysctl.conf | echo "net.core.wmem_max = 16777216" >> /etc/sysctl.conf
echo "vm.swappiness = 1" >> /etc/sysctl.conf | echo "vm.swappiness = 1" >> /etc/sysctl.conf
echo "vm.zone_reclaim_mode = 0" >> /etc/sysctl.conf | echo "vm.zone_reclaim_mode = 0" >> /etc/sysctl.conf
echo "vm.dirty_expire_centisecs = 500" >> /etc/sysctl.conf | echo "vm.dirty_expire_centisecs = 500" >> /etc/sysctl.conf
echo "vm.dirty_writeback_centisecs = 100" >> /etc/sysctl.conf | echo "vm.dirty_writeback_centisecs = 100" >> /etc/sysctl.conf
echo "### set memory parameter - more than 64GB ###" >> /etc/sysctl.conf | echo "### set memory parameter - less than 64GB ###" >> /etc/sysctl.conf
echo "vm.dirty_background_bytes = 1610612736" >> /etc/sysctl.conf | echo "vm.dirty_background_bytes = 0" >> /etc/sysctl.conf
echo "vm.dirty_background_ratio = 0" >> /etc/sysctl.conf | echo "vm.dirty_background_ratio = 3" >> /etc/sysctl.conf
echo "vm.dirty_bytes = 4294967296" >> /etc/sysctl.conf | echo "vm.dirty_bytes = 0" >> /etc/sysctl.conf
echo "vm.dirty_ratio = 0" >> /etc/sysctl.conf | echo "vm.dirty_ratio = 10" >> /etc/sysctl.conf
echo "### set gpcc reserved port ###" >> /etc/sysctl.conf | echo "### set gpcc reserved port ###" >> /etc/sysctl.conf
echo "net.ipv4.ip_local_reserved_ports=28080" >> /etc/sysctl.conf | echo "net.ipv4.ip_local_reserved_ports=28080" >> /etc/sysctl.conf
echo "### set core dump file ###" >> /etc/sysctl.conf | echo "### set core dump file ###" >> /etc/sysctl.conf
echo "kernel.core_pattern = /home/gpadmin/cores/core-%e-%s-%u-%g-%p-%t" >> /etc/sysctl.conf | echo "kernel.core_pattern = /home/gpadmin/cores/core-%e-%s-%u-%g-%p-%t" >> /etc/sysctl.conf

## sshkey_copy
[~]# cat sshkey_copy.sh
#!/bin/bash
### Usage : sh sshkey_copy.sh {hostfile_name}
source ~/.bashrc
HOST_LIST=`cat /data/staging/$1`
for host in ${HOST_LIST}
do
ssh-copy-id ${host}
done

## gpconfig
gpconfigs_set.sh |  | gpconfigs_chk.sh
### gp_vmem_protect_limit needed calculate refer pysical memory
| gpconfig -c gp_vmem_protect_limit -v 1114000 |  | gpconfig -s gp_vmem_protect_limit
| gpconfig -c gp_workfile_compression -v on --masteronly |  | gpconfig -s gp_workfile_compression
| gpconfig -c max_connections -m 500 -v 1500 |  | gpconfig -s max_connections
| gpconfig -c gp_segment_connect_timeout -v 20min |  | gpconfig -s gp_segment_connect_timeout
| gpconfig -c gp_fts_probe_timeout -v 60s |  | gpconfig -s gp_fts_probe_timeout
| gpconfig -c log_duration -v on --masteronly |  | gpconfig -s log_duration
| gpconfig -c log_min_duration_statement -v 0 --masteronly |  | gpconfig -s log_min_duration_statement
| #gpconfig -c gp_resource_manager -v "group-v2" |  | gpconfig -s gp_resource_manager
| #gpconfig -c xid_warn_limit -v 300000000 --skipvalidation |  | #gpconfig -s xid_warn_limit
| #gpconfig -c xid_stop_limit -v 200000000 --skipvalidation |  | #gpconfig -s xid_stop_limit
| #gpconfig -c max_resource_queues -v 16 --masteronly |  | #gpconfig -s max_resource_queues
| #gpconfig -c gp_resqueue_priority_cpucores_per_segment -m 64 -v 16 ### need calculate |  | #gpconfig -s gp_resqueue_priority_cpucores_per_segment
| #gpconfig -c max_appendonly_tables -v 20000 --masteronly |  | #gpconfig -s max_appendonly_tables
| #gpconfig -c max_prepared_transactions -v 500 |  | #gpconfig -s max_prepared_transactions
| #gpconfig -c superuser_reserved_connections -m 30 -v 3 |  | #gpconfig -s superuser_reserved_connections

## gpcc_conf
/home/gpadmin/gpconfigs/gpcc.conf
path = /usr/local
# Set the display_name param to the string to display in the GPCC UI.
# The default is "gpcc"
display_name = gpadmin
master_port = 5432
web_port = 28080
rpc_port = 8899
enable_ssl = false
# Uncomment and set the ssl_cert_file if you set enable_ssl to true.
# ssl_cert_file = /etc/certs/mycert
enable_kerberos = false
# Uncomment and set the following parameters if you set enable_kerberos to true.
# webserver_url = <webserver_service_url>
# krb_mode = 1
# keytab = <path_to_keytab>
# krb_service_name = postgres
# User interface language: 1=English, 2=Chinese, 3=Korean, 4=Russian, 5=Japanese
language = 1

## bashrc
cat /home/gpadmin/.bashrc
##############################
### GPDB Environment Setting
##############################
source /usr/local/greenplum-db/greenplum_path.sh
export COORDINATOR_DATA_DIRECTORY=/data/coordinator/gpseg-1
export PGPORT=5432
export PGUSER=gpadmin
export PGDATABASE=gpadmin
export LD_PRELOAD=/lib64/libz.so.1 ps
alias all='gpssh -f /home/gpadmin/gpconfigs/hostfile'
alias seg='gpssh -f /home/gpadmin/gpconfigs/hostfile_seg'

## disk_io
참조 URL : https://docs.vmware.com/en/VMware-Greenplum/7/greenplum-database/install_guide-prep_os.html#grubby_note
Disk I/O scheduler 설정 권고값
| Storage Device Type | OS | Recommended Scheduler Policy
| Non-Volatile Memory Express (NVMe) | RHEL 7 | none
|  | RHEL 8 | none
|  | Ubuntu | none
| Solid-State Drives (SSD) | RHEL 7 | noop
|  | RHEL 8 | none
|  | Ubuntu | none
| Other | RHEL 7 | deadline
|  | RHEL 8 | mq-deadline
|  | Ubuntu | mq-deadline

## network_mtu
참조 URL : https://docs.vmware.com/en/VMware-Greenplum/7/greenplum-database/install_guide-prep_os.html#grubby_note
Network 설정(MTU)
네트워크의 최대 전송 단위(MTU)는 네트워크에 연결된 장치에서 허용하는 가장 큰 데이터 패킷/프레임의 크기(바이트)를 지정합니다. 점보 프레임은 1500바이트의 표준 MTU 이상을 포함하는 프레임입니다.
Greenplum 데이터베이스는 3가지 고유한 MTU 설정을 사용합니다.
* Greenplum 데이터베이스 gp_max_packet_size 서버 구성 매개변수입니다. 기본 최대 패킷 크기는 8192입니다. 이 기본값은 점보 프레임 MTU를 가정합니다.
* 운영 체제 MTU 설정입니다.
* 랙 스위치 MTU 설정.
이러한 설정은 항상 동일하거나 동일한 값에 가까워야 하거나 MTU 크기에 대한 Greenplum < OS < 스위치의 순서로 연결되어 있습니다.
9000은 스위치에 대해 일반적으로 지원되는 설정이며 Greenplum 데이터베이스 호스트에 권장되는 OS 및 랙 스위치 MTU 설정입니다.