## 1.GPDB_upgrade
작 업 계 획 서
작업 내용 | GPDB Installation on RHEL7
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
사전 작업
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | Deploy Patch Binary | mdw | [workstation~]# scp -r gpdb 192.168.63.1:/data/staging/ | [~]# du -sh /data/staging/gpdb6210/*
2 | Directory Backup | mdw | *mdw mdw 접속
|  |  | potal 접속 후 putty 실행 | [~]$ all
|  |  | A) IP 192.168.63.1 입력 후 엔터키 입력 | => ls -al /usr/local ¦ grep '_bak'
B) User:root, Pasword:********** 입력
[~] $ all
=> sudo chmod 777 /usr/local/
=> sudo cp -r /usr/local/greenplum-db-6.11.1_bak
=> sudo chown -R gpadmin:gpadmin /usr/local/greenplum-db-6.11.1_bak
3 | Deploy GPDB 6.210 rpm | mdw | [~]$ sudo gpscp -f /home/gpadmin/gpconfig/hostfile_gpdb /data/staging/gpdb6210/greenplum-db-6.21.0-rhel7-x86_64.rpm =:/home/gpadmin
[~]$ all
=> sudo chown -R gpadmin:gpadmin /home/gpadmin
4 | Check yum repolist | mdw | [~]$ all
=> sudo yum clean all
=> sudo yum repolist
본작업
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | stop crontab, GPCC, PXF | mdw | [~]$ crontab -l > /home/gpadmin/crontab.bak
[~]$ crontab -r
[~]$ gpcc stop
2 | Stop / Start test GPDB | mdw | [~]$ gpstop -af
[~]$ gpstart -a
3 | Remove gppkgs, Stop GPDB | mdw | (1) uninstall plcontainer
[~]$ gppkg -q --all
[~]$ plcontainer runtime-delete -r plc_python_shared
[~]$ plcontainer runtime-show
|  |  | [~]$ psql {user_db} -c "DROP EXTENSION plcontainer CASCADE;" | << CASCADE는 관련 함수 사용하는 경우 필요
|  |  | [~]$ gppkg -r plcontainer-2.1.3 | DROPED OBJECT LIST는 NOTICE에 명시됨
[~]$ gppkg -q --all
(2) uninstall other gppkgs
[~]$ gppkg -q --all
[~]$ gppkg -r MetricsCollector-6.6.0_gp_6.13.0
|  |  | [~]$ psql {user_db} -c "DROP EXTENSION pljava CASCADE;" | << CASCADE는 관련 함수 사용하는 경우 필요
[~]$ gppkg -r pljava-2.0.2
|  |  | [~]$ psql {user_db} -c "DROP EXTENSION plr CASCADE;" | << CASCADE는 관련 함수 사용하는 경우 필요
[~]$ gppkg -r plr-3.0.3
[~]$ gppkg -r DataSciencePython-2.0.3
[~]$ gppkg -r DataScienceR-2.0.2
[~]$ gppkg -r madlib-1.17.0+14
[~]$ gppkg -q --all
[~]$ gpstop -af
4 | Patch GPDB 6.21.0, start GPDB | mdw | [~]# all | [~]# all
|  |  | => yum -y update /home/gpadmin/greenplum-db-6.21.0-rhel7-x86_64.rpm | => ll /usr/local ¦ grep 'grenplum-db'
=> chown -R gpadmin:gpadmin /usr/local/greenplum*
[~]$ gpstart -a
5 | Re-install PL/Java | mdw | [~}$ cd /data/staging/gpdb6210
[~}$ gppkg -i pljava-2.0.4-gp6-rhel7_x86_64.gppkg
[~}$ vi $GPHOME/greenplum_path.sh
export JAVA_HOME=/usr/lib/jvm/java-1.8.0-openjdk-1.8.0.102-4.b14el7.x86_64/jer <<< JAVA_HOME 확인
LD_LIBRARY_PATH=$JAVA_HOME/lib/amd64/server:$LD_LIBRARY_PATH <<< 수정
[~}$ gpscp -f ~/gpconfigs/hostfile_gpdb /usr/local/greenplum-db/greenplum_path.sh =:/usr/local/greenplum-db/greenplum_path.sh
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ psql {user_db} -c "CREATE EXTENSION pljava;"
6 | Re-install PL/R | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i plr-3.0.4-gp6-rhel7-x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ psql {user_db} -c "CREATE EXTENSION plr;"
7 | Re-install DataSicence Python | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i DataScincePython-2.0.4-gp6-rhel7_x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
8 | Re-install DataSicence R | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i DataScienceR-2.0.2-gp6-rhel7_x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
9 | Re-install madlib | mdw | [~]$ cd /data/staging/gpdb6210/madlib-1.19.0+1-gp6-rhel7-x86_64
[~]$ gppkg -i madlib-1.19.0+1-gp6-rhel7-x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ $GPHOME/madlib/bin/madpack install -s madlib -p greenplum -c gpadmin@{mdw_hostname}:5432/{user_db}
[~]$ $GPHOME/madlib/bin/madpack upgrade -s madlib -p greenplum -c gpadmin@{mdw_hostname}:5432/{user_db}
10 | Re-install plcontainer | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i plcontainer-2.1.5-gp6-rhel7_x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ psql {user_db} -c "CREATE EXTENSION plcontainer;"
|  |  | [~]$ plcontainer image-list | << plcontainer image 조회 여부 확인
[~]$ plcontainer runtime-add -r plc_python_shared -i pivotaldata/plcontainer_python3_shared:devel -l python3
[~]$ plcontainer runtime-show
11 | Check State GPDB | mdw | [~]$ gpstate

## 2.GPCC_upgrade
작 업 계 획 서
작업 내용 | GPDB Installation on RHEL7
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | stop gpcc {기존버전} | mdw | [~]$ gpcc --version
[~]$ gpcc stop
2 | gpcc 6.7.1 upgrade | mdw | [~]$ cd /data/staging/greenplum-cc-web-6.7.1-gp6-rhel7 -x86_64
[~]$ ./gpcinstall-6.7.1 -u
GPCC will install with existing configuration settings:
...
Would you like to continue? Yy/Nn (Default=Y)
y
INSTALLATION IN PROGRESS...
3 | gpcc version & status check | mdw | [~]$ cd /usr/local/greenplum-cc-6.7.1/gppkg
| metric collector install |  | [~]$ gppkg -i MetricsCollector-{gpcc_version}_gp_{gpdb_version}-rhel7-x86_64.gppkg | << GPCC 출시일 보다 GPDB 출시일이 나중인 경우
|  |  | [~]$ source ~/.bash_profile | metric collector gppkg 설치 불필요
[~]$ gpcc --version
[~]$ gpcc start
[~]$ gpcc status
[~]$ gpcc stop
4 | gpdb restart | mdw | [~]$ gpstop -af
| gpcc parametsr 확인 |  | [~]$ gpstart -a
[~]$ gpconfig -s gpcc.enable_send_instrument
[~]$ gpconfig -s gpcc.enable_send_lock_info
5 | start gpcc 6.7.1 | mdw | [~]$ gpcc start
6 | gpcc parameter 값 변경 | mdw | [~]$ gpconfig -c gpcc.enable_send_instrument -v 'off' | << GPCC 메모리 과점유 문제 있을 경우
|  |  | [~]$ gpconfig -c gpcc.enable_send_lock_info -v 'off' | gpcc 관련 파라메터 설정 off 로 변경
7 | gpcc parameter 적용 | mdw | [~]$ gpstop -u | << gpcc 관련 파라메터 온라인 적용
8 | gpcc parameter 확인 | mdw | [~]$ gpconfig -s gpcc.enable_send_instrument
[~]$ gpconfig -s gpcc.enable_send_lock_info
9 | remove gpcc {기존버전} | mdw | [~] # all
=> /bin/rm -rf /usr/localgreenplum-cc-web[기존번전]

## 3.PXF6_upgrade
작 업 계 획 서
작업 내용 | GPDB Installation on RHEL7
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | 기존 pxf5 디렉토리 backup | mdw | [~]$ all | [~]$ all
|  |  | => /bin/cp -r /usr/local/greenplum-db-6.13.0_bak/pxf /usr/local/greenplum-db-6.13.0_bak/pxf_{작업년월일} | => ll /usr/local/greenplum-db.6.11.1/pxf_{수행날짜}
2 | pxf 6.3.1 설치파일 배포 | mdw | [~]# cd /data/staging/gpdb6210/
[~]# gpscp -f /home/gpadmin/gpconfigs/hostfile pxf-gp6-6.3.1-2.el7.x86_64.rpm =:/home/gpadmin/pxf-gp6-6.3.1-2.el7.x86_64.rpm
[~]# all
=> chown gpadmin:gpadmin /home/gpadmin/pxf-gp6-6.3.1-2.el7.x86_64.rpm
=> ls -al /home/gpadmin/pxf-gp6-*.rpm
3 | pxf 6.3.1 설치 | mdw | [~]# all | [~]# all
|  |  | => yum clean all | => rpm -qa ¦ grep pxf
|  |  | => yum repolist | => ls -al /usr/local/ ¦ grep pxf-gp6
=> rpm -Uvh /home/gpadmin/pxf-gp6-6.3.1-2.el7.x86_64.rpm
=> chown -R gpadmin:gpadmin /usr/local/pxf-gp6
4 | pxf migrate | mdw | [~]$ echo $PXF_CONF
|  |  | [~]$ /usr/local/pxf-gp6/bin/pxf cluster migrate | [~]$ /usr/local/pxf-gp6/bin/pxf cluster migrate
Migrating PXF configuration on master host and 4 segment hosts...
PXF configuration migrated successfully on 5 out of 5 hosts
|  |  | [~]$ /usr/local/pxf-gp6/bin/pxf cluster register | [~]$ /usr/local/pxf-gp6/bin/pxf cluster register
Installing PXF extension on master host and 4 segment hosts...
PXF extension has been installed on 5 out of 5 hosts
5 | pxf extension 생성 & 권한 설정 | mdw | [~]$ psql {user_db} -c "select * from pg_available_extensions where name = 'pxf';"
[~]$ psql {user_db} -c "create extension pxf;"
[~]$ psql {user_db} -c "alter extension pxf update;"
[~]$ psql {user_db} -c "select * from pg_available_extensions where name = 'pxf';"
[~]$ psql {user_db} -c "grant all on protocol pxf to public;"
6 | .bashrc 수정 | mdw | [~]$ vi ~/.bashrc | gpadmin .bashrc에 환경변수 추가
export PATH=$PATH:/usr/local/pxf-gp6/bin
export PXF_CONF=/usr/local/pxf-gp6
[~]$ source ~/.bashrc
7 | .bash_profile 수정 | mdw | [~]$ vi ~/.bash_profile | gpadmin .bash_profile에 pxf alias 변경
### pxf6 alias 재설정
alias pxfstatus='/usr/local/pxf-gp6/bin/pxf cluster status'
alias pxfstart='/usr/local/pxf-gp6/bin/pxf cluster start'
alias pxfstop='/usr/local/pxf-gp6/bin/pxf cluster stop'
alias pxfsync='/usr/local/pxf-gp6/bin/pxf cluster sync'
alias pxfregister='/usr/local/pxf-gp6/bin/pxf cluster register'
alias pxfreset='/usr/local/pxf-gp6/bin/pxf cluster reset'
[~]$ source ~/.bash_profile
8 | pxf cluster register, start | mdw | [~]$ /usr/local/pxf-gp6/bin/pxf cluster register
[~]$ /usr/local/pxf-gp6/bin/pxf cluster sync
[~]$ /usr/local/pxf-gp6/bin/pxf cluster start
9 | pxf 상태 및 version 확인 | mdw | [~]$ /usr/local/pxf-gp6/bin/pxf cluster status
[~]$ /usr/local/pxf-gp6/bin/pxf version

## 4.scram_sha_256
작 업 계 획 서
작업 내용 | GPDB Installation on RHEL7
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | GPDB stop 사전 준비 | mdw | # GPCC Web Monitoring Service 중지 | * crontab, gpcc, pxf, pgbouncer stop
[~]$ gpcc stop
# PXF External Table Service 중지
[~]$ /usr/local/pxf-gp6/bin/pxf cluster stop
# pgbouncer 중지
[~]$ pgbstop
2 | GPDB Parameter 변경 | mdw | # SCRAM-SHA-256 Parameter 변경 (변경 값은 GPDB 재기동 후에 적용 됨)
[~]$ gpconfig -c password_hash_algorithm -v 'SCRAM-SHA-256'
# GPDB 중지
[~]$ gpstop -af
# GPDB 시작
[~]$ gpstart -a
3 | 기존 user password 재설정 | mdw | # SCRAM-SHA-256 형식 적요을 위한 user Pasword 재설정 | # 기존 MD5 에서 SCRAM-SHA-256 형식으로 변경 확인
|  |  | [~]$ sh /home/gpadmin/alteruser_password.sh | [~]$ psql -tc "select '\"' ¦¦ rolname ¦¦ '\" \"' ¦¦ case when rolpasword is null then '' else rolpasword end ¦¦ '\"' from pg_authid;"
#! /bin/bash << 모든 유저 패스워드 변경
source /usr/local/greenplum-db/greenplum_path.sh
psql -c "alter user gpadmin with password 'changeme';"
psql -c "alter user gpmon with password 'changeme';"
psql -c "alter user gpi_user with password 'changeme';"
.....
4 | pg_hba.conf 편집 | mdw | # 기존 pg_hba.conf Backup | # 기존 pg_hba.conf Backup 라인 카운트르 통해 확인
|  |  | [~]$ cat $MASTER_DATA_DIRECTORY/pg_hba.conf $MASTER_DATA_DIRECTORY/pg_hba.conf_bak | [~]$ cat $MASTER_DATA_DIRECTORY/pg_hba.conf_bak ¦ wc -l
(라인수)
|  |  | # pg_hba.conf 내용중 md5 문자를 scram-sha-256 문자로 치환 | # pg_hba.conf 내용중 md5 문자를 검색하여 결과없음 확인
|  |  | [~]$ sed -i 's/md5/scram-sha-256/g' $MASTER_DATA_DIRECTORY/pg_hba.conf | [~]$ cat $MASTER_DATA_DIRECTORY/pg_hba.conf ¦ grep md5
(결과 없음)
# pg_hba.conf reload 하여변경 값 적용
[~]$ gpstop -u
5 | crontab, gpcc, pxf start | mdw | # Crontab 원복
[~]$ crontab /home/gpadmin/crontab.bak
#GPCC Web Monitoring Service 시작
[~]$ gpcc start
# PXF External Table Service 시작
[~]$ /usr/local/pxf-gp6/bin/pxf cluster start
6 | pgbouncer ini 수정 | mdw | # pgbouncer ini SCRAM-SHA-256으로 변경 | # Auth type 변경 확인
|  |  | [~]$ vi /data/master/pgbouncer/pgbouncer.ini | [~]$ cat /data/master/pgbouncer/pgbouncer.ini ¦ grep auth_type
auth_type = SCRAM-SHA-256
7 | pgbouncer user 정보 변경 | mdw | # pgbouncer user 정보 SCRAM-SHA-256 형식으로 생성
|  |  | [~]$ psql -tc "select '\"' ¦¦ rolname ¦¦ '\" \"' ¦¦ case when rolpassword is null then '' else rolpassword end ¦¦ | [~]$ cat /data/master/pgbouncer/pgbouncer.user
\"' from pg_authid;" > /data/master/pgbouncer/pgbouncer.usr
8 | pgbouncer 시작 | mdw | # pgbouncer 시작
|  |  | [~]$ pgbstart | #pgbouncer 시작 확인
[~]$ pgbp

## 5.pxf_test
작 업 계 획 서
작업 내용 | GPDB Installation on RHEL7
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
본작업
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | Test EXTERNAL TABLE | mdw | [~]$ psql
SELECT * FROM test1_lake1 limit 0;
|  |  | … | <<< select 정상조회 확인
DROP EXTERNAL TABLE IF EXISTS test1_lake1;
CREATE EXTERNAL TABLE test1_lake1
( line_id text )
LOCATION (
pxf://Datalake/test1_lake1_*.csv?PROFILE=hdfs:text&SERVER=datalake1' )
FORMAT 'csv' (delimiter E'~' null E'NULL' escape E'"' quote E'"')
ENCODING 'UTF8'
SEGMENT REJECT LIMIT 10000 ROWS;
SELECT * FROM test1_lake1 limit 10;
SELECT * FROM test2_lake2 limit 10;
|  |  | … | <<< select 정상조회 확인
DROP EXTERNAL TABLE IF EXISTS test2_lake2;
CREATE EXTERNAL TABLE test2_lake2
( line_id text )
LOCATION (
pxf://Datalake/test2_lake2_*.deflate?PROFILE=hdfs:text&SERVER=datalake2' )
FORMAT 'csv' (delimiter E'~' null E'NULL' escape E'"' quote E'"')
ENCODING 'UTF8'
SEGMENT REJECT LIMIT 10000 ROWS;
SELECT * FROM test2_lake2 limit 10;
* 임시 Test 테이블은 Drop 수행
DROP EXTERNAL TABLE IF EXIST test1_lake1;
DROP EXTERNAL TABLE IF EXIST test2_lake2;
사후 작업
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
2 | Remove grenplum-db-6.7.1, | mdw | [~]# all
| greenplum-cc-web-6.2.0 |  | => rm -rf /usr/local/greenplum-db-6.11.1 | [~}$ ll /usr/local/greenplum-db-6.11.1
(결과 없음)
3 | Change ownership local dir | mdw | [~]# all
|  |  | => chmod 755 /usr/local | [~]$ ll /usr ¦ grep local

## 99.minor_upgrade
작 업 계 획 서
작업 내용 | GPDB Installation on RHEL7
사전 준비 | 자료 URL에서 다운로드 받은 파일을 /data/staging 으로 복사
자료 URL | https://github.com/zhyun-pivotal/gpdb6_install
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | Deploy Patch Binary | mdw | [workstation~]# scp -r gpdb 192.168.63.1:/data/staging/ | [~]# du -sh /data/staging/gpdb6210/*
2 | Directory Backup | mdw | *mdw mdw 접속
|  |  | potal 접속 후 putty 실행 | [~]$ all
|  |  | A) IP 192.168.63.1 입력 후 엔터키 입력 | => ls -al /usr/local ¦ grep '_bak'
B) User:root, Pasword:********** 입력
[~] $ all
>sudo chmod 777 /usr/local/
=>sudo cp -r /usr/local/greenplum-db-6.11.1_bak
=>sudo chown -R gpadmin:gpadmin /usr/local/greenplum-db-6.11.1_bak
3 | Deploy GPDB 6.210 rpm | mdw | [~]$ sudo gpscp -f /home/gpadmin/gpconfig/hostfile_gpdb /data/staging/gpdb6210/greenplum-db-6.21.0-rhel7-x86_64.rpm =:/home/gpadmin
[~]$ all
=> sudo chown -R gpadmin:gpadmin /home/gpadmin
4 | Check yum repolist | mdw | [~]$ all
=> sudo yum clean all
=> sudo yum repolist
본작업
작 업 계 획
seq | 작업내용 | 작업대상 | 작업자에 의한 사전 작업 내용 | 검증방법
1 | stop crontab, GPCC, PXF | mdw | [~]$ crontab -l > /home/gpadmin/crontab.bak
[~]$ crontab -r
[~]$ gpcc stop
2 | Stop / Start test GPDB | mdw | [~]$ gpstop -af
[~]$ gpstart -a
3 | Remove gppkgs, Stop GPDB | mdw | [~]$ psql gpperfmon -c `drop extension metrics_collector' | [~]$ gppkg -q --all
[~]$ gppkg -r MetricsCollector-6.7.1_gp_6.11.1
[~]$ gppkg -q --all
[~]$ psql mes -c 'drop extention pljava'
[~]$ gppkf -r plr-3.0.3
[~]$ gppkg -r DataSciencePython-2.0.3
[~]$ gppkg -r DataScienceR-2.0.2
[~]$ gppkg -r madlib-1.17.0+14 << 미설치 시 생략
[~]$gpstop -af
4 | Patch GPDB 6.21.0, start GPDB | mdw | [~]# all | [~]# all
|  |  | => sudo yum -y update /home/gpadmin/greenplum-db-6.21.0-rhel7-x86_64.rpm | => ll /usr/local ¦ grep 'grenplum-db'
=> chown -R gpadmin:gpadmin /usr/local/greenplum*
[~]$ gpstart -a
5 | Start GPCC 및 gpcc Parameter 확인 | mdw | [~]$ cd /usr/local/greenplum-cc-6.7.1/gppkg
| <GPCC 6.7.1 사전 설치 완료> |  | [~]$ vi ~/.bach_profile <<< 아래 내요을 .bash_profile에 수정
source /usr/local/greenplum-cc/gpcc_path.sh
export GPPERFMONHOME=/usr/local/greenplum-cc
[~]$ source ~/.bash_profile
[~]$ gpc start
[~]$ gpc --version
[~}$ gpconfig -s gpcc.enable_send_instrument
[~}$ gpconfig -s gpcc.enable_send_lock_info
6 | Re-install PL/Java | mdw | [~}$ cd /data/staging/gpdb6210
[~}$ gppkg -i pljava-2.0.4-gp6-rhel7_x86_64.gppkg
[~}$ vi $GPHOME/greenplum_path.sh
export JAVA_HOME=/usr/lib/jvm/java-1.8.0-openjdk-1.8.0.102-4.b14el7.x86_64/jer
LD_LIBRARY_PATH=$JAVA_HOME/lib/amd64/server:$LD_LIBRARY_PATH <<< 내용 입력
[~}$ gpscp -f ~/gpconfig/hostfile_gpdb /usr/local/greenplum-db/greenplum_path.sh =:/usr/local/greenplum-db/grenplum_path.sh
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ psql
db=# CREATE EXTENSION pljava;
7 | Re-install PL/R | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i plr-3.0.4-gp6-rhel7-x86_64.gppkg
[~]$ source /usr/local/greenplum-db/grenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ psql
db=# CREATE EXTENSION plr;
8 | Re-install DataSicence Python | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i DataScincePython-2.0.4-gp6-rhel7_x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
9 | Re-install DataSicence R | mdw | [~]$ cd /data/staging/gpdb6210
[~]$ gppkg -i DataScienceR-2.0.2-gp6-rhel7_x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
10 | Re-install madlib | mdw | [~]$ cd /data/staging/gpdb6210/madlib-1.19.0+1-gp6-rhel7-x86_64
| <미사용 시 생략> |  | [~]$ gppkg -i madlib-1.19.0+1-gp6-rhel7-x86_64.gppkg
[~]$ source /usr/local/greenplum-db/greenplum_path.sh
[~]$ gpstop -af
[~]$ gpstart -a
[~]$ $GPHOME/madlib/bin/madpack install -s madlib -p greenplum -c gpadmin@{MDW서버명}:5432/mes
[~]$ $GPHOME/madlib/bin/madpack upgrade -s madlib -p greenplum -c gpadmin@{MDW서버명}:5432/mes
11 | Check State GPDB | mdw | [~]$ gpstate