## Cover
[ SOP(Standard Operation Procedure) ]
개정이력표
버전 | 날짜 | 내 용 | 담당자
1.0 | 2023-03-30 | catalog vacuum full | 현지수
활용 용도 및 작성 방법
설치, 증설, 재구성, 유지보수(Upgrade, Break/Fix 포함), 변경작업, 프로젝트 세부 작업 계획과 관련된 표준화된 작업 문서로 활용 가능
장애발생 후 긴급 서비스 정상화/안정화를 목적으로 하는 경우는 제외

## catalog_vacuum_full_before_6.19
작 업 계 획 서
[12 empty] | 작성자 | 작성일자
[12 empty] | 검토자(HW/OS) | 검토일자
작업 내용 | GPDB catalog vacuum full | [10 empty] | 검토자(DB/SW) | 검토일자
사전 준비
자료 URL
범례 | [~]# : root 계정으로 실행
| [~]$ : gpadmin 계정으로 실행 | [10 empty] | 고객성함 | 최종 Review일자
작 업 계 획 | [9 empty] | 전체작업소요시간 | 0:00 | 검 토 | 작업후 확인 결과 및 Follow-up 사항
날짜 | 대분류 | 설치 구분 | Service | Task | 중분류 | 작업 | 소분류 | 확인 사항 | 비고
| (HW/SW/ETC) |  | (Up/Down) | # | (Task) | 노드 | (세부 작업 내용, Commands 포함)
| SW | N/A | Up | 1 | 사전 bloat 점검 | mdw | [~]$ cd ~/dba |  |  |  | 0:00
[7 empty] | [~]$ psql -f chk_catalog_bloat.sql > chk_catalog_bloat.before |  | * chk_catalog_bloat 시트 참조
| SW | N/A | Down | 2 | crontab, gpcc, pxf stop | mdw | [~]$ crontab -l > /home/gpadmin/crontab.bak |  |  |  | 0:00
[~]$ cat /home/gpadmin/crontab.bak ¦ wc -l
63
[~]$ crontab -r
[~]$ crontab -l
no crontab for gpadmin
[~]$ gpcc stop
2023-03-30 16:40:57 Stopping the gpcc agents and webserver…
2023-03-30 16:40:59 GPCC webserver and metrics collection agents have been stopped.
[~] $GPHOME/pxf/bin/pxf cluster stop
Stopping PXF on 16 segment hosts…
PXF stoppped successfully on 16 out of 16 hots
| SW | N/A | Down | 3 | GPDB stop | mdw | [~]$ gpstop -af
[~]$ all
=> ps -ef ¦ grep postgres ¦ grep -v grep ¦ wc -l
0
=> ipcs ¦ grep gpadmin ¦ grep -v grep ¦ wc -l
0
=> ls -alrth /tmp ¦ grep PGSQL ¦ grep -v grep ¦ wc -l
0
| SW | N/A | Down | 4 | GPDB start w/restricted mode | mdw | [~]$ gpstart -aR
20230330:10:58:24:002618 gpstart:gm1:gpadmin-[INFO]:-Starting gpstart with args: -aR
20230330:10:58:24:002618 gpstart:gm1:gpadmin-[INFO]:-Gathering information and validating the environment...
...
20230330:10:58:25:002618 gpstart:gm1:gpadmin-[INFO]:-Starting Master instance gm1 directory /data/master/gpseg-1 in RESTRICTED mode
20230330:10:58:25:002618 gpstart:gm1:gpadmin-[INFO]:-Command pg_ctl reports Master gm1 instance active
20230330:10:58:25:002618 gpstart:gm1:gpadmin-[INFO]:-Connecting to dbname='template1' connect_timeout=15
20230330:10:58:26:002618 gpstart:gm1:gpadmin-[INFO]:-Starting standby master
20230330:10:58:26:002618 gpstart:gm1:gpadmin-[INFO]:-Checking if standby master is running on host: gm2 in directory: /data/master/gpseg-1
20230330:10:58:26:002618 gpstart:gm1:gpadmin-[INFO]:-Database successfully started
| SW | N/A | Down | 5 | Catalog Table vacuum full | mdw | [~]$ cd /home/gpadmin/utilities
[~]$ mkdir -p /home/gpadmin/utilities/log
[7 empty] | [~]$ vi vacuum_full_analyze.sh |  | * vacuum_full_analyze 시트 참조
[~]$ cat vacuum_full_analyze.sh
…
[8 empty] | DBNAME="gpadmin" | * DBNAME 항목값을 작업 대상 DB로 변경
DATE="/bin/date"
ECHO="/bin/echo"
LOGFILE="/data/utilities/log/vacuum_full_analyze_`date '+%Y-%m-%d'`.log"
…
[~]$ nohup sh vacuum_full_analyze.sh &
[~]$ tail -n 50 -f /data/utilities/log/vacuum_full_analyze_$(date '+%Y-%m-%d').log
| SW | N/A | Down | 6 | GPDB stop | mdw | [~]$ gpstop -af
[~]$ all
=> ps -ef ¦ grep postgres ¦ grep -v grep ¦ wc -l
0
=> ipcs ¦ grep gpadmin ¦ grep -v grep ¦ wc -l
0
=> ls -alrth /tmp ¦ grep PGSQL ¦ grep -v grep ¦ wc -l
0
| SW | N/A | Down | 8 | GPDB start w/normal mode | mdw | [~]$ gpstart -a
20230330:11:41:58:003498 gpstart:gm1:gpadmin-[INFO]:-Starting gpstart with args: -a
20230330:11:41:58:003498 gpstart:gm1:gpadmin-[INFO]:-Gathering information and validating the environment...
...
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Starting Master instance gm1 directory /data/master/gpseg-1
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Command pg_ctl reports Master gm1 instance active
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Connecting to dbname='template1' connect_timeout=15
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Starting standby master
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Checking if standby master is running on host: gm2 in directory: /data/master/gpseg-1
20230330:11:42:00:003498 gpstart:gm1:gpadmin-[INFO]:-Database successfully started
| SW | N/A | Down | 9 | crontab, gpcc, pxf start | mdw | [~]$ crontab /home/gpadmin/crontab.bak
[~]$ crontab -l
6
[~]$ gpcc start
2023-03-30 16:04:31 Starting the gpcc agents and webserver…
2023-03-30 16:04:35 GPCC webserver and metrics collection agents have been started.
[~]$ $GPHOME/pxf/bin/pxf cluster start
Starting PXF on 16 segment hosts…
PXF started successfully on 16 out of 16 hots
| SW | N/A | Up | 10 | 사후 bloat 점검 | mdw | [~]$ cd ~/dba |  |  |  | 0:00
[7 empty] | [~]$ psql -f chk_catalog_bloat.sql > chk_catalog_bloat.after |  | * chk_catalog_bloat 시트 참조

## catalog_vacuum_full_after_6.19
작 업 계 획 서
[12 empty] | 작성자 | 작성일자
[12 empty] | 검토자(HW/OS) | 검토일자
작업 내용 | GPDB catalog vacuum full | [10 empty] | 검토자(DB/SW) | 검토일자
사전 준비
자료 URL
범례 | [~]# : root 계정으로 실행
| [~]$ : gpadmin 계정으로 실행 | [10 empty] | 고객성함 | 최종 Review일자
작 업 계 획 | [9 empty] | 전체작업소요시간 | 0:00 | 검 토 | 작업후 확인 결과 및 Follow-up 사항
날짜 | 대분류 | 설치 구분 | Service | Task | 중분류 | 작업 | 소분류 | 확인 사항 | 비고
| (HW/SW/ETC) |  | (Up/Down) | # | (Task) | 노드 | (세부 작업 내용, Commands 포함)
| SW | N/A | Up | 1 | 사전 bloat 점검 | mdw | [~]$ cd ~/dba |  |  |  | 0:00
[7 empty] | [~]$ psql -f chk_catalog_bloat.sql > chk_catalog_bloat.before |  | * chk_catalog_bloat 시트 참조
| SW | N/A | Down | 2 | crontab, gpcc, pxf stop | mdw | [~]$ crontab -l > /home/gpadmin/crontab.bak |  |  |  | 0:00
[~]$ cat /home/gpadmin/crontab.bak ¦ wc -l
63
[~]$ crontab -r
[~]$ crontab -l
no crontab for gpadmin
[~]$ gpcc stop
2023-03-30 16:40:57 Stopping the gpcc agents and webserver...
2023-03-30 16:40:59 GPCC webserver and metrics collection agents have been stopped. Use gpcc start to start them again
[~] /usr/local/pxf-gp6/bin/pxf cluster stop
Stopping PXF on master host, standby master host, and 4 segment hosts...
PXF stopped successfully on 6 out of 6 hosts
| SW | N/A | Down | 3 | GPDB stop | mdw | [~]$ gpstop -af
[~]$ all
=> ps -ef ¦ grep postgres ¦ grep -v grep ¦ wc -l
0
=> ipcs ¦ grep gpadmin ¦ grep -v grep ¦ wc -l
0
=> ls -alrth /tmp ¦ grep PGSQL ¦ grep -v grep ¦ wc -l
0
| SW | N/A | Down | 4 | GPDB start w/restricted mode | mdw | [~]$ gpstart -aR
20230330:10:58:24:002618 gpstart:gm1:gpadmin-[INFO]:-Starting gpstart with args: -aR
20230330:10:58:24:002618 gpstart:gm1:gpadmin-[INFO]:-Gathering information and validating the environment...
...
20230330:10:58:25:002618 gpstart:gm1:gpadmin-[INFO]:-Starting Master instance gm1 directory /data/master/gpseg-1 in RESTRICTED mode
20230330:10:58:25:002618 gpstart:gm1:gpadmin-[INFO]:-Command pg_ctl reports Master gm1 instance active
20230330:10:58:25:002618 gpstart:gm1:gpadmin-[INFO]:-Connecting to dbname='template1' connect_timeout=15
20230330:10:58:26:002618 gpstart:gm1:gpadmin-[INFO]:-Starting standby master
20230330:10:58:26:002618 gpstart:gm1:gpadmin-[INFO]:-Checking if standby master is running on host: gm2 in directory: /data/master/gpseg-1
20230330:10:58:26:002618 gpstart:gm1:gpadmin-[INFO]:-Database successfully started
| SW | N/A | Down | 5 | Catalog Table vacuum full | mdw | [~]$ cd /home/gpadmin/utilities
[~]$ mkdir -p /home/gpadmin/utilities/log
[7 empty] | [~]$ vi vacuum_full_analyze.sh |  | * vacuum_full_analyze 시트 참조
[~]$ cat vacuum_full_analyze.sh
…
[8 empty] | DBNAME="gpadmin" | * DBNAME 항목값을 작업 대상 DB로 변경
DATE="/bin/date"
ECHO="/bin/echo"
LOGFILE="/data/utilities/log/vacuum_full_analyze_`date '+%Y-%m-%d'`.log"
…
[~]$ nohup sh vacuum_full_analyze.sh &
[~]$ tail -n 50 -f /data/utilities/log/vacuum_full_analyze_$(date '+%Y-%m-%d').log
| SW | N/A | Down | 6 | GPDB stop | mdw | [~]$ gpstop -af
[~]$ all
=> ps -ef ¦ grep postgres ¦ grep -v grep ¦ wc -l
0
=> ipcs ¦ grep gpadmin ¦ grep -v grep ¦ wc -l
0
=> ls -alrth /tmp ¦ grep PGSQL ¦ grep -v grep ¦ wc -l
0
| SW | N/A | Down | 8 | GPDB start w/normal mode | mdw | [~]$ gpstart -a
20230330:11:41:58:003498 gpstart:gm1:gpadmin-[INFO]:-Starting gpstart with args: -a
20230330:11:41:58:003498 gpstart:gm1:gpadmin-[INFO]:-Gathering information and validating the environment...
...
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Starting Master instance gm1 directory /data/master/gpseg-1
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Command pg_ctl reports Master gm1 instance active
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Connecting to dbname='template1' connect_timeout=15
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Starting standby master
20230330:11:41:59:003498 gpstart:gm1:gpadmin-[INFO]:-Checking if standby master is running on host: gm2 in directory: /data/master/gpseg-1
20230330:11:42:00:003498 gpstart:gm1:gpadmin-[INFO]:-Database successfully started
| SW | N/A | Down | 9 | crontab, gpcc, pxf start | mdw | [~]$ crontab /home/gpadmin/crontab.bak
[~]$ crontab -l
6
[~]$ gpcc start
2023-03-30 16:04:31 Starting the gpcc agents and webserver...
2023-03-30 16:04:35 Agent successfully started on 6/6 hosts
2023-03-30 16:04:35 View Greenplum Command Center at http://testgm1:28080
[~]$ /usr/local/pxf-gp6/bin/pxf cluster start
Starting PXF on master host, standby master host, and 4 segment hosts...
PXF started successfully on 6 out of 6 hosts
| SW | N/A | Up | 10 | 사후 bloat 점검 | mdw | [~]$ cd ~/dba |  |  |  | 0:00
[7 empty] | [~]$ psql -f chk_catalog_bloat.sql > chk_catalog_bloat.after |  | * chk_catalog_bloat 시트 참조

## chk_catalog_bloat
/home/gpadmin/dba/chk_catalog_bloat.sql
select a.*
from (
select n.nspname as schemaname,
c.relname as tablename,
b.btdrelpages as actual_pages,
b.btdexppages as expected_pages,
round(pg_relation_size(n.nspname ¦¦ '.' ¦¦ c.relname)/1024/1024) as actual_size_mb,
round(pg_relation_size(n.nspname ¦¦ '.' ¦¦ c.relname)/1024/1024 * b.btdexppages/b.btdrelpages) as expected_size_mb
from gp_toolkit.gp_bloat_expected_pages as b
join pg_class as c
on c.oid=b.btdrelid
join pg_namespace as n
on c.relnamespace=n.oid
where b.btdrelpages > 1
and n.nspname in ('pg_catalog') ) as a
--where actual_size_mb > 1
--and actual_size_mb / expected_size_mb > 1
order by 1,2 desc ;

## vacuum_full_analyze
/home/gpadmin/utilities/vacuum_full_analyze.sh
#!/bin/bash
if [ -f /home/gpadmin/.bash_profile ]; then
. /home/gpadmin/.bash_profile
fi
DBNAME="gpdemo"
DATE="/bin/date"
ECHO="/bin/echo"
LOGFILE="/data/utilities/log/vacuum_full_analyze_`date '+%Y-%m-%d'`.log"
$ECHO "CTALOG TABLE VACUUM FULL ANALYZE started at " > $LOGFILE
$DATE >> $LOGFILE
$ECHO ".............................." >> $LOGFILE
VCOMMAND="VACUUM FULL VERBOSE"
psql -tc "select '$VCOMMAND' ¦¦ ' pg_catalog.' ¦¦ relname ¦¦ ';' from pg_class a, pg_namespace b where a.relnamespace=b.oid and b.nspname='pg_catalog' and a.relkind='r'" $DBNAME ¦ psql -a $DBNAME >> $LOGFILE
$ECHO ".............................." >> $LOGFILE
VCOMMAND="ANALYZE"
psql -tc "select '$VCOMMAND' ¦¦ ' pg_catalog.' ¦¦ relname ¦¦ ';' from pg_class a, pg_namespace b where a.relnamespace=b.oid and b.nspname='pg_catalog' and a.relkind='r'" $DBNAME ¦ psql -a $DBNAME >> $LOGFILE
$ECHO ".............................." >> $LOGFILE
reindexdb -s >> $LOGFILE
$ECHO ".............................." >> $LOGFILE
$ECHO "CATALOG TABLE VACUUM FULL ANALYZE completed at " >> $LOGFILE
$DATE >> $LOGFILE